## Column Mapping
Sprint/Phase | Purpose | File | Sheet | Column(s) Used | Notes
Sprint 0 (Discovery) | Plan & execute Discovery cadence | Sprint Plan - Template.xlsx | Board-Project tasks | Task number, Outline number, Sprint Name, Work Item type, WorkItem Status, Work Items Description, Assigned to, Effort, Duration, Start, Finish, Story Points, Priority, Milestone, % complete | Core sprint backlog & day-to-day tasks.
Sprint 0 (Discovery) | Capture risks & mitigations | Config_board-projecttsk.xlsx | Sheet1 | Risk Type, Risk Severity, Risk Mitigation Strategy | Use when demonstrating 'audit stress test' & governance questions.
Sprint 0 (Discovery) | Define required data items / traceability | Config_Dataitems_CMS.xlsx | Config_Dataitems_CMS | Configuration Item Name, Item Type, Data Type, Is Mandatory, Applies To, Description | Use to list required upstream fields to support BC audit trail.
Sprint 0 (Discovery) | Confirm resource model & availability | Master_Resourse_config.xlsx | Master_Resourse_config | Resource Name, Role/Function, Skillset/Expertise, Availability Status, Allocation Percentage, Location | Supports CEO question: 'Is it only you or a team?'
All sprints | Executive progress roll-up / KPI view | Consolidated_PMData_Demo.xlsx | Allinone | Project Name, Task Status, Task Priority, % Complete, KPIs, Risk Level, Project Budget, Budget Utilized | Optional — use for a leadership snapshot / dashboard export.
Sprint 1 (BC Foundation) | BC tenant + finance foundations tasks | Sprint Plan - Template.xlsx | Board-Project tasks | Work Items Description + Goal + Milestone + Completed | Populate with BC-CORE backlog IDs and sprint goal.
Sprint 2 (Transactional MVP) | Integration contract + traceability tasks | Sprint Plan - Template.xlsx | Board-Project tasks | Work Items Description + Work Item type + Milestone | Populate with BC-TX backlog IDs.

## Board-Project tasks
Task number | Outline number | Sprint Name | Work Item type | WorkItem Status | Work Items Description | Assigned to | Effort | Duration | Start | Story Points | Finish | Effort remaining | Priority | % complete | Effort completed | Milestone | Completed | Goal | __PowerAppsId__
BC-DISC-01 | 1.1 | Sprint 0 – Discovery | Epic | Not Started | Ecosystem map: systems touching finance + owners | Zeeshan / Client SME | 8 | 1 | 2026-02-02 | 3 | 2026-02-02 | 8 | 1 | 0% | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing | BcF4NtAWnAA
BC-DISC-02 | 1.2 | Sprint 0 – Discovery | Story | Not Started | Financial data lineage: order→invoice→GL trace (current state) | Zeeshan + Finance SME | 8 | 1 | 2026-02-03 | 3 | 2026-02-03 | 8 | 1 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-03 | 1.3 | Sprint 0 – Discovery | Story | Not Started | Audit stress-test: trace one invoice backwards; identify control gaps | Zeeshan + Finance Lead | 8 | 1 | 2026-02-04 | 5 | 2026-02-04 | 8 | 1 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-04 | 1.4 | Sprint 0 – Discovery | Story | Not Started | Integration contract draft: required fields + validation rules | Zeeshan + Tech SME | 6 | 1 | 2026-02-05 | 5 | 2026-02-05 | 6 | 2 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-05 | 1.5 | Sprint 0 – Discovery | Task | Not Started | Decisions log: BC ownership boundaries (what must exist in BC) | Zeeshan | 4 | 1 | 2026-02-06 | 3 | 2026-02-06 | 4 | 2 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-06 | 2.1 | Sprint 0 – Discovery | Story | Not Started | Sequencing options: upstream fixes vs BC build order (recommendation) | Zeeshan | 6 | 1 | 2026-02-09 | 5 | 2026-02-09 | 6 | 1 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-07 | 2.2 | Sprint 0 – Discovery | Task | Not Started | Risk register v1 + mitigation plan | Zeeshan + Client | 4 | 1 | 2026-02-10 | 3 | 2026-02-10 | 4 | 2 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-08 | 2.3 | Sprint 0 – Discovery | Task | Not Started | Discovery readout pack: maps + risks + decisions + next steps | Zeeshan | 6 | 1 | 2026-02-11 | 5 | 2026-02-11 | 6 | 1 | 0 | 0 |  | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-DISC-GATE | 2.4 | Sprint 0 – Discovery | Milestone | Not Started | Decision gate: approve Phase 2 scope / backlog / owners | CEO + Sponsor | 2 | 1 | 2026-02-12 | 1 | 2026-02-12 | 2 | 1 | 0 | 0 | Discovery Gate: Go / Pause / Re-sequence | No | Confirm BC authority-of-record, data lineage, risks, and phase sequencing
BC-CORE-01 | 3.1 | Sprint 1 – BC Foundation (MVG) | Epic | Not Started | BC tenant/company setup + environments (Dev/Test) | Zeeshan | 6 | 2 | 2026-02-16 | 5 | 2026-02-17 | 6 | 1 | 0 | 0 |  | No | Stand up BC finance core with guardrails (control rules, dimensions, posting)
BC-CORE-02 | 3.2 | Sprint 1 – BC Foundation (MVG) | Story | Not Started | Chart of Accounts + posting setup aligned to audit needs | Finance Lead + Zeeshan | 8 | 3 | 2026-02-18 | 8 | 2026-02-20 | 8 | 1 | 0 | 0 |  | No | Stand up BC finance core with guardrails (control rules, dimensions, posting)
BC-CORE-03 | 3.3 | Sprint 1 – BC Foundation (MVG) | Story | Not Started | Dimensions model (simple, scalable) + reporting structure | Zeeshan + Finance | 6 | 2 | 2026-02-21 | 5 | 2026-02-22 | 6 | 2 | 0 | 0 |  | No | Stand up BC finance core with guardrails (control rules, dimensions, posting)
BC-CORE-04 | 3.4 | Sprint 1 – BC Foundation (MVG) | Story | Not Started | Approval workflows + period close controls (MVG) | Zeeshan | 6 | 2 | 2026-02-23 | 5 | 2026-02-24 | 6 | 2 | 0 | 0 |  | No | Stand up BC finance core with guardrails (control rules, dimensions, posting)
BC-CORE-05 | 3.5 | Sprint 1 – BC Foundation (MVG) | Milestone | Not Started | Foundation demo: BC can reject invalid data (validation rules) | Zeeshan + Client | 2 | 1 | 2026-02-26 | 1 | 2026-02-26 | 2 | 1 | 0 | 0 | BC Foundation Ready | No | Stand up BC finance core with guardrails (control rules, dimensions, posting)
BC-TX-01 | 4.1 | Sprint 2 – Transactional MVP | Epic | Not Started | Define transactional model: order lines, pricing, tax, discounts | Zeeshan + SMEs | 6 | 2 | 2026-03-02 | 5 | 2026-03-03 | 6 | 1 | 0 | 0 |  | No | Achieve traceable invoice lifecycle (order model + integration validations)
BC-TX-02 | 4.2 | Sprint 2 – Transactional MVP | Story | Not Started | Integration contract v1 implemented (field mapping + validations) | Zeeshan + Dev | 8 | 3 | 2026-03-04 | 8 | 2026-03-06 | 8 | 1 | 0 | 0 |  | No | Achieve traceable invoice lifecycle (order model + integration validations)
BC-TX-03 | 4.3 | Sprint 2 – Transactional MVP | Story | Not Started | Invoice generation / validation in BC (no blind summaries) | Zeeshan + Finance | 8 | 3 | 2026-03-08 | 8 | 2026-03-10 | 8 | 1 | 0 | 0 |  | No | Achieve traceable invoice lifecycle (order model + integration validations)
BC-TX-04 | 4.4 | Sprint 2 – Transactional MVP | Task | Not Started | Exception handling: reconciliation + dispute workflow | Zeeshan | 6 | 2 | 2026-03-11 | 5 | 2026-03-12 | 6 | 2 | 0 | 0 |  | No | Achieve traceable invoice lifecycle (order model + integration validations)
BC-TX-05 | 4.5 | Sprint 2 – Transactional MVP | Milestone | Not Started | Proof: trace 1 invoice end-to-end with audit trail | CEO/Sponsor + Finance | 2 | 1 | 2026-03-12 | 1 | 2026-03-12 | 2 | 1 | 0 | 0 | Traceability MVP Proven | No | Achieve traceable invoice lifecycle (order model + integration validations)

## Sheet1
Work Item ID | unique identifier to be assicaited with an item and should be added as a mandatory information - example 1.0
Sprint Name | Sprints are usually named as Sp1 or Sprint 1 , so that we have all wokring items associated to a working pipeline - a sprint is isusally 2 weeks so when proposing the working schedule you should consider the dates and time line accordingly
Work Item Type | It the the type of work such as , Epic , User story or Task
WorkItem Status | Work items state, such as In progress, Not strated, complete , blocker
Work Items Description | THe deatils of the work item - should be added as a mandotory info to this template as it will provide the information of work that is required
Assigned to | Resource that will be working on that item during the sprint , but when an item is not active, it should be in the backlog state and no resoruce assinged to it
Effort | Effort is estimated in hours and then calculated as days if needed, so for example an item is going to take 4 days , it will mean that we need 32 hours as each days has 8 working hours in it
Duration | Duration is days so when a work item is estimated, the days should entered here
Start | This field should have the start date of the workitem as to when the work from the resource shouild be started. this should be with in the Sprint dates that are upto 2 weeks each
Story Points | use the complexity rule we dicssuced to add the estimated number - example 2 being the least complex , and 10 being the most complex
Finish | According to the effort that is added in the Effort column, the date should be automaticallyh added hhere - example if the stat date is 12- dec - 2024 and the Effort estimated is 2 days then the calcualtion should retrun as "start + duration = Finish" which will be 12-dec-2024 + 2 = 14-dec-2024
Priority | high, medum , low
% Complete | should be left as blank as the % of work is not calculated in the begning of the project
Goal | the should show the goal that is associted with this work item - so use the Goals information you gather from the breif document and add it to the work item relavnt to it

## OurGoals
UID | Goal Name | Priority | Status | Start date | End date | Connected tasks | Description
GL-1000 | Enhance User Experience During Initial Setup |  | DL |  |  |  | Specific: Design and implement an intuitive setup wizard that guides administrators through the initial configuration process. Measurable: Achieve a user satisfaction score of 90% or higher in post-setup surveys. Achievable: Utilize user feedback and iterative testing to refine the setup wizard. Relevant: A smooth setup process is crucial for user adoption and satisfaction. Time-bound: Complete the implementation and testing of the setup wizard within 3 months.
GL-1001 | Integrate Seamlessly with Existing Systems |  | DL |  |  |  | Specific: Ensure the help desk module integrates with Azure AD, Microsoft Teams, and other essential systems. Measurable: Achieve 100% integration with the specified systems and ensure no critical integration issues are reported. Achievable: Collaborate with system architects and use established APIs and integration protocols. Relevant: Integration with existing systems is essential for operational efficiency and data consistency. Time-bound: Complete all integrations within 4 months.
GL-1002 | Utilize Learning Models for Improved Efficiency |  | DL |  |  |  | Specific: Implement learning models to optimize ticket management and provide accurate recommendations. Measurable: Reduce average ticket resolution time by 20% within 6 months of implementation. Achievable: Leverage existing data and machine learning algorithms to build effective models. Relevant: Improved efficiency in ticket management directly impacts customer satisfaction and support team productivity. Time-bound: Develop and deploy learning models within 5 months.
GL-1003 | Ensure Continuous Improvement and Customization |  | DL |  |  |  | Specific: Provide mechanisms for user feedback and customization options for the help desk module. Measurable: Implement a feedback system and achieve at least 50 actionable feedback submissions within the first 3 months post-launch. Achievable: Integrate feedback collection into the user interface and establish a process for analyzing and acting on feedback. Relevant: Continuous improvement and customization are key to maintaining relevance and user satisfaction. Time-bound: Implement feedback and customization features within 3 months.
GL-1004 | Standardize Incident and Service Request Categorization |  | DL |  |  |  | Specific: Develop and implement industry-specific categorizations for incidents and service requests based on ITIL principles. Measurable: Achieve a 90% accuracy rate in auto-categorizing incidents and service requests within 3 months of deployment. Achievable: Use predefined ITIL categorizations and refine them based on user feedback and real-world data. Relevant: Standardized categorization ensures consistency and efficiency in handling support requests. Time-bound: Finalize and deploy categorization standards within 4 months.
GL-1005 | Efficiently Manage Devices and User Assets |  | DL |  |  |  | Specific: Implement a robust device and asset management system within the help desk module. Measurable: Achieve 100% tracking and management of devices and assets with no critical discrepancies within the first 3 months post-implementation. Achievable: Utilize Azure AD and device discovery tools to automate asset tracking and management. Relevant: Effective device management is crucial for resolving technical issues and maintaining asset records. Time-bound: Complete the implementation and testing of the device management system within 4 months.

## GoaltoUS maper
Goal | Description | Time-bound | EPIC-UID | Epics | User Stories
1 | Enhance User Experience During Initial Setup | 3 months | EPC-0001 | Gather Basic Business Information, Configure System Based on User and Business Information | User Story 1, User Story 2, User Story 3, User Story 4, User Story 5
2 | Integrate Seamlessly with Existing Systems | 4 months | EPC-0002 | Integrate Existing Processes and Systems, Device Integration and Asset Management | User Story 6, User Story 7, User Story 21, User Story 22, User Story 23
3 | Utilize Learning Models for Improved Efficiency | 5 months | EPC-0003 | Utilize Learning Models and Generate Knowledge Base | User Story 8, User Story 9
4 | Ensure Continuous Improvement and Customization | 3 months | EPC-0004 | Provide Customization and Continuous Improvement | User Story 10, User Story 11
5 | Standardize Incident and Service Request Categorization | 4 months | EPC-0005 | Associating Questions with Data Sets and Criteria, Implementing Criteria-Based Configuration | User Story 12, User Story 13, User Story 14, User Story 15, User Story 16, User Story 17, User Story 18
6 | Efficiently Manage Devices and User Assets | 4 months | EPC-0006 | Device Integration and Asset Management | User Story 21, User Story 23, User Story 24, User Story 25
Summary of Goals and Corresponding Epics/User Stories

## Config
UID | WorkItem | Descp | UID
WI-0001 | EPIC | These are high-level themes that group related user stories.
WI-0002 | User Story | Describe individual features or functionality to be developed.
WI-0003 | Admin | Tasks related to administrative setup and configuration.
WI-0004 | Feature | Specific capabilities or enhancements within the product.
WI-0005 | Testcase | Conditions or scenarios to validate the functionality.
WI-0006 | Issue | Problems or bugs that need to be addressed.
WI-0007 | Goal | Broad outcomes that the project aims to achieve.
WI-0008 | Objective | Specific, measurable steps towards achieving the goals.
WI-0009 | Note | Additional information or reminders related to the project.