## FactTasks
TaskID | TaskName | Description | ModuleID | PriorityID | TypeID | OwnerID | StatusID | Phase | StartDate | DueDate | CompletedDate | CompletionPct | EffortHoursEst | EffortHoursActual | Risk | Milestone | Notes
SYS-001 | Create users & permission sets | Define roles; assign permission sets; test access | 1 | 1 | 1 | 3 | 2 | Build | 2026-05-12 | 2026-05-19 |  | 60 | 6 | 4 | Medium | Sandbox ready
SYS-002 | Configure email accounts | SMTP/Graph email; test document sending | 1 | 2 | 1 | 3 | 1 | Build |  | 2026-05-29 |  | 0 | 3 | 0 | Low
SYS-003 | Set up approval workflows (basic) | Approvals for purchase invoices and payments | 1 | 2 | 2 | 8 | 1 | Build | 2026-05-28 | 2026-06-05 |  | 0 | 8 | 0 | Medium
SYS-004 | Audit & security review | Review data access; admin accounts; MFA guidance | 1 | 1 | 2 | 3 | 1 | Test | 2026-05-31 | 2026-06-07 |  | 0 | 6 | 0 | Medium
CMP-001 | Company information | Address, VAT reg no, bank details, local settings | 2 | 1 | 1 | 8 | 5 | Build | 2026-05-05 | 2026-05-06 | 2026-05-06 | 100 | 2 | 2 | Low
CMP-002 | Number series | Customers, vendors, items, documents, journals | 2 | 1 | 1 | 8 | 2 | Build | 2026-05-07 | 2026-05-16 |  | 70 | 6 | 4 | Medium
CMP-003 | Base calendar | Working days, holidays, shipping calendar | 2 | 2 | 2 | 8 | 1 | Build | 2026-05-26 | 2026-06-02 |  | 0 | 2 | 0 | Low
FIN-001 | Chart of Accounts review | Adopt UK COA or tailor; account categories | 3 | 1 | 1 | 2 | 2 | Build | 2026-05-08 | 2026-05-18 |  | 80 | 12 | 10 | Medium
FIN-002 | General Posting Groups | Gen. Bus/Prod posting groups codes | 3 | 1 | 1 | 8 | 2 | Build | 2026-05-16 | 2026-05-23 |  | 50 | 8 | 4 | High | Core setup complete
FIN-003 | General Posting Setup matrix | Map posting groups to GL accounts | 3 | 1 | 1 | 8 | 1 | Build | 2026-05-24 | 2026-05-31 |  | 0 | 10 | 0 | High
FIN-004 | Accounting periods | Create fiscal year periods; close rules | 3 | 2 | 1 | 2 | 5 | Build | 2026-05-14 | 2026-05-14 | 2026-05-14 | 100 | 2 | 1 | Low
FIN-005 | Payment terms & methods | 30DAYS/COD; payment methods; reminders | 3 | 2 | 1 | 2 | 2 | Build | 2026-05-20 | 2026-05-28 |  | 30 | 4 | 1 | Low
FIN-006 | Dimensions | DEPT & PROJECT; default dimensions; rules | 3 | 1 | 1 | 8 | 1 | Build | 2026-05-29 | 2026-06-05 |  | 0 | 8 | 0 | Medium
VAT-001 | VAT posting groups | VAT Bus/Prod posting groups (DOMESTIC, STANDARD etc) | 4 | 1 | 1 | 2 | 2 | Build | 2026-05-17 | 2026-05-21 |  | 60 | 6 | 3 | High
VAT-002 | VAT Posting Setup matrix | 20% standard; accounts; VAT identifiers | 4 | 1 | 1 | 2 | 1 | Build | 2026-05-25 | 2026-06-01 |  | 0 | 10 | 0 | High
VAT-003 | VAT statement & return settings | VAT statement layout; reporting periods | 4 | 2 | 2 | 2 | 1 | Test | 2026-05-28 | 2026-06-07 |  | 0 | 6 | 0 | Medium
BNK-001 | Bank accounts | Create bank accounts; posting groups; formats | 5 | 1 | 1 | 2 | 1 | Build | 2026-05-26 | 2026-06-02 |  | 0 | 6 | 0 | Medium
BNK-002 | Bank reconciliation setup | Import formats; reconcile rules | 5 | 2 | 2 | 2 | 1 | Test | 2026-05-31 | 2026-06-10 |  | 0 | 8 | 0 | Medium
SAL-001 | Customer posting groups | Create customer posting groups and mapping | 6 | 1 | 1 | 2 | 2 | Build | 2026-05-19 | 2026-05-24 |  | 60 | 6 | 3 | High
SAL-002 | Customer templates | Templates incl posting groups, VAT groups | 6 | 2 | 2 | 4 | 1 | Build | 2026-05-27 | 2026-06-03 |  | 0 | 4 | 0 | Low
SAL-003 | Contacts & interactions (Customer Centre) | Import contacts; link to customers; roles | 6 | 2 | 2 | 4 | 1 | Build | 2026-05-29 | 2026-06-07 |  | 0 | 8 | 0 | Medium
SAL-004 | Sales document setup | No. series; posting; shipment/invoice settings | 6 | 1 | 1 | 8 | 1 | Build | 2026-05-28 | 2026-06-04 |  | 0 | 8 | 0 | Medium
SAL-005 | Sales prices/discounts (basic) | Price groups; line discounts (optional) | 6 | 3 | 2 | 4 | 1 | Optimise | 2026-06-02 | 2026-06-15 |  | 0 | 6 | 0 | Low
PUR-001 | Vendor posting groups | Create vendor posting groups and mapping | 7 | 1 | 1 | 2 | 2 | Build | 2026-05-19 | 2026-05-24 |  | 60 | 6 | 3 | High
PUR-002 | Purchase document setup | No. series; posting; receipt/invoice settings | 7 | 1 | 1 | 8 | 1 | Build | 2026-05-28 | 2026-06-04 |  | 0 | 8 | 0 | Medium
PUR-003 | Purchase approvals (if needed) | Approval users; limits; workflows | 7 | 2 | 2 | 8 | 1 | Test | 2026-05-31 | 2026-06-10 |  | 0 | 6 | 0 | Medium
INV-001 | Inventory setup | Costing method (FIFO); inventory periods | 8 | 1 | 1 | 6 | 2 | Build | 2026-05-20 | 2026-05-25 |  | 70 | 6 | 4 | High
INV-002 | Units of measure | PCS etc; item units | 8 | 1 | 1 | 6 | 5 | Build | 2026-05-18 | 2026-05-18 | 2026-05-18 | 100 | 2 | 1 | Low
INV-003 | Item categories | Categories; posting groups; dimensions defaults | 8 | 2 | 2 | 6 | 1 | Build | 2026-05-27 | 2026-06-03 |  | 0 | 4 | 0 | Low
INV-004 | Inventory posting setup | Inventory posting groups and mapping | 8 | 1 | 1 | 8 | 1 | Build | 2026-05-28 | 2026-06-05 |  | 0 | 10 | 0 | High
INV-005 | Import item master | Import items; validate; pictures (optional) | 8 | 1 | 1 | 14 | 1 | Build | 2026-06-01 | 2026-06-11 |  | 0 | 12 | 0 | Medium | Master data imported
INV-006 | Adjust cost / cost posting test | Run Adjust Cost; verify GL impact | 8 | 2 | 1 | 8 | 1 | Test | 2026-06-07 | 2026-06-17 |  | 0 | 6 | 0 | Medium
WH-001 | Locations | Create locations; policies | 9 | 2 | 2 | 6 | 1 | Build | 2026-06-03 | 2026-06-13 |  | 0 | 6 | 0 | Low
WH-002 | Bins (if used) | Bin setup; directed pick/put-away | 9 | 3 | 2 | 6 | 4 | Optimise | 2026-06-10 | 2026-06-30 |  | 0 | 12 | 0 | Low
HR-001 | Employee records | Create/import employees; departments | 10 | 2 | 2 | 7 | 1 | Build | 2026-06-05 | 2026-06-15 |  | 0 | 8 | 0 | Low
HR-002 | HR posting integration | Set up salary journals mapping (if used) | 10 | 3 | 2 | 2 | 4 | Optimise | 2026-06-13 | 2026-07-05 |  | 0 | 10 | 0 | Low
FA-001 | Fixed asset setup | FA posting groups; depreciation books | 11 | 2 | 2 | 2 | 4 | Build | 2026-06-13 | 2026-07-05 |  | 0 | 10 | 0 | Low
PRJ-001 | Jobs/Projects setup | Job nos; posting; dimensions | 12 | 3 | 2 | 8 | 4 | Build | 2026-06-15 | 2026-07-10 |  | 0 | 12 | 0 | Low
PBI-001 | Define KPI catalogue | Agree KPIs and dashboards (exec/ops) | 13 | 1 | 1 | 9 | 2 | Design | 2026-05-24 | 2026-05-31 |  | 50 | 8 | 4 | Medium
PBI-002 | Power BI data model | Star schema; measures; data dictionary | 13 | 1 | 1 | 9 | 1 | Build | 2026-05-30 | 2026-06-09 |  | 0 | 12 | 0 | Medium
PBI-003 | Build dashboard pages | Exec summary; Finance; Sales; Project; Risks | 13 | 1 | 1 | 9 | 1 | Build | 2026-06-05 | 2026-06-19 |  | 0 | 16 | 0 | Medium | First dashboard draft
PBI-004 | Refresh & governance | Refresh schedule; RLS; workspace structure | 13 | 2 | 2 | 9 | 4 | Deploy | 2026-06-15 | 2026-06-30 |  | 0 | 10 | 0 | Medium
MIG-001 | Migration mapping | Source→BC mapping; templates; cleansing rules | 14 | 1 | 1 | 8 | 2 | Design | 2026-05-16 | 2026-05-23 |  | 70 | 12 | 8 | High
MIG-002 | Trial import #1 | Import master data to sandbox; fix errors | 14 | 1 | 1 | 8 | 2 | Build | 2026-05-24 | 2026-05-31 |  | 40 | 16 | 10 | High
MIG-003 | Trial import #2 | Repeat import after fixes; validate posting | 14 | 1 | 1 | 8 | 1 | Build | 2026-06-01 | 2026-06-09 |  | 0 | 16 | 0 | Medium
MIG-004 | Opening balances | GL, AR/AP opening balances via journals | 14 | 1 | 1 | 2 | 4 | Deploy | 2026-06-09 | 2026-06-23 |  | 0 | 16 | 0 | High
TST-001 | Test scripts | End-to-end scripts (sales/purchase/GL/VAT) | 15 | 1 | 1 | 10 | 2 | Test | 2026-05-21 | 2026-05-28 |  | 70 | 10 | 7 | Medium
TST-002 | System integration testing | Execute scripts; log defects | 15 | 1 | 1 | 10 | 1 | Test | 2026-05-29 | 2026-06-09 |  | 0 | 20 | 0 | High
TST-003 | UAT | Business sign-off; training feedback | 15 | 1 | 1 | 10 | 1 | Test | 2026-06-07 | 2026-06-21 |  | 0 | 24 | 0 | High | UAT sign-off
GOL-001 | Cutover plan | Runbook; freeze dates; communications | 16 | 1 | 1 | 1 | 1 | Deploy | 2026-06-13 | 2026-06-25 |  | 0 | 12 | 0 | High
GOL-002 | Production migration | Run final import; reconcile totals | 16 | 1 | 1 | 8 | 1 | Deploy | 2026-06-20 | 2026-06-28 |  | 0 | 20 | 0 | High
GOL-003 | Go-live readiness review | Checklist: access, posting, VAT, reports | 16 | 1 | 1 | 1 | 1 | Deploy | 2026-06-23 | 2026-06-29 |  | 0 | 6 | 0 | High | Go-live
PGL-001 | Hypercare | Daily triage; defect fixes; adoption support | 17 | 1 | 1 | 1 | 1 | Optimise | 2026-06-30 | 2026-07-14 |  | 0 | 30 | 0 | Medium
PGL-002 | Month-end close rehearsal | Close checklist; reconciliations; reporting | 17 | 2 | 2 | 2 | 4 | Optimise | 2026-07-10 | 2026-07-25 |  | 0 | 16 | 0 | Medium

## DimModule
ModuleID | Module | ModuleSort
1 | System & Security | 1
2 | Company Setup | 2
3 | Finance - Core | 3
4 | VAT & Tax (UK) | 4
5 | Banking & Cash | 5
6 | Sales & Customer Centre | 6
7 | Purchasing | 7
8 | Inventory & Items | 8
9 | Warehouse | 9
10 | Human Resources | 10
11 | Fixed Assets | 11
12 | Projects/Jobs | 12
13 | Reporting & Power BI | 13
14 | Data Migration | 14
15 | Testing & UAT | 15
16 | Go-Live | 16
17 | Post-Go-Live | 17

## DimOwner
OwnerID | Owner | Function | Team
1 | Project Manager | PMO | Programme
2 | Finance Lead | Finance | Business
3 | IT Admin | IT | Technology
4 | Sales Admin | Sales | Business
5 | Purchasing Lead | Procurement | Business
6 | Inventory Lead | Operations | Business
7 | HR Admin | HR | Business
8 | BC Consultant | Partner | Delivery
9 | BI Analyst | BI | Technology
10 | Test Lead | QA | Delivery

## DimPriority
PriorityID | Priority | PrioritySort
1 | High | 1
2 | Medium | 2
3 | Low | 3

## DimType
TypeID | Type
1 | Essential
2 | Optional

## DimStatus
StatusID | Status | StatusSort | IsClosed
1 | Not Started | 1 | 0
2 | In Progress | 2 | 0
3 | Blocked | 3 | 0
4 | On Hold | 4 | 0
5 | Done | 5 | 1

## DimDate
Date | Year | MonthName | Month | Quarter | Week | DayName | IsWeekend
2025-05-26 | 2025 | May | 5 | 2025Q2 | 22 | Monday | 0
2025-05-27 | 2025 | May | 5 | 2025Q2 | 22 | Tuesday | 0
2025-05-28 | 2025 | May | 5 | 2025Q2 | 22 | Wednesday | 0
2025-05-29 | 2025 | May | 5 | 2025Q2 | 22 | Thursday | 0
2025-05-30 | 2025 | May | 5 | 2025Q2 | 22 | Friday | 0
2025-05-31 | 2025 | May | 5 | 2025Q2 | 22 | Saturday | 1
2025-06-01 | 2025 | June | 6 | 2025Q2 | 22 | Sunday | 1
2025-06-02 | 2025 | June | 6 | 2025Q2 | 23 | Monday | 0
2025-06-03 | 2025 | June | 6 | 2025Q2 | 23 | Tuesday | 0
2025-06-04 | 2025 | June | 6 | 2025Q2 | 23 | Wednesday | 0
2025-06-05 | 2025 | June | 6 | 2025Q2 | 23 | Thursday | 0
2025-06-06 | 2025 | June | 6 | 2025Q2 | 23 | Friday | 0
2025-06-07 | 2025 | June | 6 | 2025Q2 | 23 | Saturday | 1
2025-06-08 | 2025 | June | 6 | 2025Q2 | 23 | Sunday | 1
2025-06-09 | 2025 | June | 6 | 2025Q2 | 24 | Monday | 0
2025-06-10 | 2025 | June | 6 | 2025Q2 | 24 | Tuesday | 0
2025-06-11 | 2025 | June | 6 | 2025Q2 | 24 | Wednesday | 0
2025-06-12 | 2025 | June | 6 | 2025Q2 | 24 | Thursday | 0
2025-06-13 | 2025 | June | 6 | 2025Q2 | 24 | Friday | 0
2025-06-14 | 2025 | June | 6 | 2025Q2 | 24 | Saturday | 1
2025-06-15 | 2025 | June | 6 | 2025Q2 | 24 | Sunday | 1
2025-06-16 | 2025 | June | 6 | 2025Q2 | 25 | Monday | 0
2025-06-17 | 2025 | June | 6 | 2025Q2 | 25 | Tuesday | 0
2025-06-18 | 2025 | June | 6 | 2025Q2 | 25 | Wednesday | 0
2025-06-19 | 2025 | June | 6 | 2025Q2 | 25 | Thursday | 0
2025-06-20 | 2025 | June | 6 | 2025Q2 | 25 | Friday | 0
2025-06-21 | 2025 | June | 6 | 2025Q2 | 25 | Saturday | 1
2025-06-22 | 2025 | June | 6 | 2025Q2 | 25 | Sunday | 1
2025-06-23 | 2025 | June | 6 | 2025Q2 | 26 | Monday | 0
2025-06-24 | 2025 | June | 6 | 2025Q2 | 26 | Tuesday | 0
2025-06-25 | 2025 | June | 6 | 2025Q2 | 26 | Wednesday | 0
2025-06-26 | 2025 | June | 6 | 2025Q2 | 26 | Thursday | 0
2025-06-27 | 2025 | June | 6 | 2025Q2 | 26 | Friday | 0
2025-06-28 | 2025 | June | 6 | 2025Q2 | 26 | Saturday | 1
2025-06-29 | 2025 | June | 6 | 2025Q2 | 26 | Sunday | 1
2025-06-30 | 2025 | June | 6 | 2025Q2 | 27 | Monday | 0
2025-07-01 | 2025 | July | 7 | 2025Q3 | 27 | Tuesday | 0
2025-07-02 | 2025 | July | 7 | 2025Q3 | 27 | Wednesday | 0
2025-07-03 | 2025 | July | 7 | 2025Q3 | 27 | Thursday | 0
2025-07-04 | 2025 | July | 7 | 2025Q3 | 27 | Friday | 0
2025-07-05 | 2025 | July | 7 | 2025Q3 | 27 | Saturday | 1
2025-07-06 | 2025 | July | 7 | 2025Q3 | 27 | Sunday | 1
2025-07-07 | 2025 | July | 7 | 2025Q3 | 28 | Monday | 0
2025-07-08 | 2025 | July | 7 | 2025Q3 | 28 | Tuesday | 0
2025-07-09 | 2025 | July | 7 | 2025Q3 | 28 | Wednesday | 0
2025-07-10 | 2025 | July | 7 | 2025Q3 | 28 | Thursday | 0
2025-07-11 | 2025 | July | 7 | 2025Q3 | 28 | Friday | 0
2025-07-12 | 2025 | July | 7 | 2025Q3 | 28 | Saturday | 1
2025-07-13 | 2025 | July | 7 | 2025Q3 | 28 | Sunday | 1
2025-07-14 | 2025 | July | 7 | 2025Q3 | 29 | Monday | 0
2025-07-15 | 2025 | July | 7 | 2025Q3 | 29 | Tuesday | 0
2025-07-16 | 2025 | July | 7 | 2025Q3 | 29 | Wednesday | 0
2025-07-17 | 2025 | July | 7 | 2025Q3 | 29 | Thursday | 0
2025-07-18 | 2025 | July | 7 | 2025Q3 | 29 | Friday | 0
2025-07-19 | 2025 | July | 7 | 2025Q3 | 29 | Saturday | 1
2025-07-20 | 2025 | July | 7 | 2025Q3 | 29 | Sunday | 1
2025-07-21 | 2025 | July | 7 | 2025Q3 | 30 | Monday | 0
2025-07-22 | 2025 | July | 7 | 2025Q3 | 30 | Tuesday | 0
2025-07-23 | 2025 | July | 7 | 2025Q3 | 30 | Wednesday | 0
2025-07-24 | 2025 | July | 7 | 2025Q3 | 30 | Thursday | 0
2025-07-25 | 2025 | July | 7 | 2025Q3 | 30 | Friday | 0
2025-07-26 | 2025 | July | 7 | 2025Q3 | 30 | Saturday | 1
2025-07-27 | 2025 | July | 7 | 2025Q3 | 30 | Sunday | 1
2025-07-28 | 2025 | July | 7 | 2025Q3 | 31 | Monday | 0
2025-07-29 | 2025 | July | 7 | 2025Q3 | 31 | Tuesday | 0
2025-07-30 | 2025 | July | 7 | 2025Q3 | 31 | Wednesday | 0
2025-07-31 | 2025 | July | 7 | 2025Q3 | 31 | Thursday | 0
2025-08-01 | 2025 | August | 8 | 2025Q3 | 31 | Friday | 0
2025-08-02 | 2025 | August | 8 | 2025Q3 | 31 | Saturday | 1
2025-08-03 | 2025 | August | 8 | 2025Q3 | 31 | Sunday | 1
2025-08-04 | 2025 | August | 8 | 2025Q3 | 32 | Monday | 0
2025-08-05 | 2025 | August | 8 | 2025Q3 | 32 | Tuesday | 0
2025-08-06 | 2025 | August | 8 | 2025Q3 | 32 | Wednesday | 0
2025-08-07 | 2025 | August | 8 | 2025Q3 | 32 | Thursday | 0
2025-08-08 | 2025 | August | 8 | 2025Q3 | 32 | Friday | 0
2025-08-09 | 2025 | August | 8 | 2025Q3 | 32 | Saturday | 1
2025-08-10 | 2025 | August | 8 | 2025Q3 | 32 | Sunday | 1
2025-08-11 | 2025 | August | 8 | 2025Q3 | 33 | Monday | 0
2025-08-12 | 2025 | August | 8 | 2025Q3 | 33 | Tuesday | 0
2025-08-13 | 2025 | August | 8 | 2025Q3 | 33 | Wednesday | 0
2025-08-14 | 2025 | August | 8 | 2025Q3 | 33 | Thursday | 0
2025-08-15 | 2025 | August | 8 | 2025Q3 | 33 | Friday | 0
2025-08-16 | 2025 | August | 8 | 2025Q3 | 33 | Saturday | 1
2025-08-17 | 2025 | August | 8 | 2025Q3 | 33 | Sunday | 1
2025-08-18 | 2025 | August | 8 | 2025Q3 | 34 | Monday | 0
2025-08-19 | 2025 | August | 8 | 2025Q3 | 34 | Tuesday | 0
2025-08-20 | 2025 | August | 8 | 2025Q3 | 34 | Wednesday | 0
2025-08-21 | 2025 | August | 8 | 2025Q3 | 34 | Thursday | 0
2025-08-22 | 2025 | August | 8 | 2025Q3 | 34 | Friday | 0
2025-08-23 | 2025 | August | 8 | 2025Q3 | 34 | Saturday | 1
2025-08-24 | 2025 | August | 8 | 2025Q3 | 34 | Sunday | 1
2025-08-25 | 2025 | August | 8 | 2025Q3 | 35 | Monday | 0
2025-08-26 | 2025 | August | 8 | 2025Q3 | 35 | Tuesday | 0
2025-08-27 | 2025 | August | 8 | 2025Q3 | 35 | Wednesday | 0
2025-08-28 | 2025 | August | 8 | 2025Q3 | 35 | Thursday | 0
2025-08-29 | 2025 | August | 8 | 2025Q3 | 35 | Friday | 0
2025-08-30 | 2025 | August | 8 | 2025Q3 | 35 | Saturday | 1
2025-08-31 | 2025 | August | 8 | 2025Q3 | 35 | Sunday | 1
2025-09-01 | 2025 | September | 9 | 2025Q3 | 36 | Monday | 0
2025-09-02 | 2025 | September | 9 | 2025Q3 | 36 | Tuesday | 0
2025-09-03 | 2025 | September | 9 | 2025Q3 | 36 | Wednesday | 0
2025-09-04 | 2025 | September | 9 | 2025Q3 | 36 | Thursday | 0
2025-09-05 | 2025 | September | 9 | 2025Q3 | 36 | Friday | 0
2025-09-06 | 2025 | September | 9 | 2025Q3 | 36 | Saturday | 1
2025-09-07 | 2025 | September | 9 | 2025Q3 | 36 | Sunday | 1
2025-09-08 | 2025 | September | 9 | 2025Q3 | 37 | Monday | 0
2025-09-09 | 2025 | September | 9 | 2025Q3 | 37 | Tuesday | 0
2025-09-10 | 2025 | September | 9 | 2025Q3 | 37 | Wednesday | 0
2025-09-11 | 2025 | September | 9 | 2025Q3 | 37 | Thursday | 0
2025-09-12 | 2025 | September | 9 | 2025Q3 | 37 | Friday | 0
2025-09-13 | 2025 | September | 9 | 2025Q3 | 37 | Saturday | 1
2025-09-14 | 2025 | September | 9 | 2025Q3 | 37 | Sunday | 1
2025-09-15 | 2025 | September | 9 | 2025Q3 | 38 | Monday | 0
2025-09-16 | 2025 | September | 9 | 2025Q3 | 38 | Tuesday | 0
2025-09-17 | 2025 | September | 9 | 2025Q3 | 38 | Wednesday | 0
2025-09-18 | 2025 | September | 9 | 2025Q3 | 38 | Thursday | 0
2025-09-19 | 2025 | September | 9 | 2025Q3 | 38 | Friday | 0
2025-09-20 | 2025 | September | 9 | 2025Q3 | 38 | Saturday | 1
2025-09-21 | 2025 | September | 9 | 2025Q3 | 38 | Sunday | 1
2025-09-22 | 2025 | September | 9 | 2025Q3 | 39 | Monday | 0
2025-09-23 | 2025 | September | 9 | 2025Q3 | 39 | Tuesday | 0
2025-09-24 | 2025 | September | 9 | 2025Q3 | 39 | Wednesday | 0
2025-09-25 | 2025 | September | 9 | 2025Q3 | 39 | Thursday | 0
2025-09-26 | 2025 | September | 9 | 2025Q3 | 39 | Friday | 0
2025-09-27 | 2025 | September | 9 | 2025Q3 | 39 | Saturday | 1
2025-09-28 | 2025 | September | 9 | 2025Q3 | 39 | Sunday | 1
2025-09-29 | 2025 | September | 9 | 2025Q3 | 40 | Monday | 0
2025-09-30 | 2025 | September | 9 | 2025Q3 | 40 | Tuesday | 0
2025-10-01 | 2025 | October | 10 | 2025Q4 | 40 | Wednesday | 0
2025-10-02 | 2025 | October | 10 | 2025Q4 | 40 | Thursday | 0
2025-10-03 | 2025 | October | 10 | 2025Q4 | 40 | Friday | 0
2025-10-04 | 2025 | October | 10 | 2025Q4 | 40 | Saturday | 1
2025-10-05 | 2025 | October | 10 | 2025Q4 | 40 | Sunday | 1
2025-10-06 | 2025 | October | 10 | 2025Q4 | 41 | Monday | 0
2025-10-07 | 2025 | October | 10 | 2025Q4 | 41 | Tuesday | 0
2025-10-08 | 2025 | October | 10 | 2025Q4 | 41 | Wednesday | 0
2025-10-09 | 2025 | October | 10 | 2025Q4 | 41 | Thursday | 0
2025-10-10 | 2025 | October | 10 | 2025Q4 | 41 | Friday | 0
2025-10-11 | 2025 | October | 10 | 2025Q4 | 41 | Saturday | 1
2025-10-12 | 2025 | October | 10 | 2025Q4 | 41 | Sunday | 1
2025-10-13 | 2025 | October | 10 | 2025Q4 | 42 | Monday | 0
2025-10-14 | 2025 | October | 10 | 2025Q4 | 42 | Tuesday | 0
2025-10-15 | 2025 | October | 10 | 2025Q4 | 42 | Wednesday | 0
2025-10-16 | 2025 | October | 10 | 2025Q4 | 42 | Thursday | 0
2025-10-17 | 2025 | October | 10 | 2025Q4 | 42 | Friday | 0
2025-10-18 | 2025 | October | 10 | 2025Q4 | 42 | Saturday | 1
2025-10-19 | 2025 | October | 10 | 2025Q4 | 42 | Sunday | 1
2025-10-20 | 2025 | October | 10 | 2025Q4 | 43 | Monday | 0
2025-10-21 | 2025 | October | 10 | 2025Q4 | 43 | Tuesday | 0
2025-10-22 | 2025 | October | 10 | 2025Q4 | 43 | Wednesday | 0
2025-10-23 | 2025 | October | 10 | 2025Q4 | 43 | Thursday | 0
2025-10-24 | 2025 | October | 10 | 2025Q4 | 43 | Friday | 0
2025-10-25 | 2025 | October | 10 | 2025Q4 | 43 | Saturday | 1
2025-10-26 | 2025 | October | 10 | 2025Q4 | 43 | Sunday | 1
2025-10-27 | 2025 | October | 10 | 2025Q4 | 44 | Monday | 0
2025-10-28 | 2025 | October | 10 | 2025Q4 | 44 | Tuesday | 0
2025-10-29 | 2025 | October | 10 | 2025Q4 | 44 | Wednesday | 0
2025-10-30 | 2025 | October | 10 | 2025Q4 | 44 | Thursday | 0
2025-10-31 | 2025 | October | 10 | 2025Q4 | 44 | Friday | 0
2025-11-01 | 2025 | November | 11 | 2025Q4 | 44 | Saturday | 1
2025-11-02 | 2025 | November | 11 | 2025Q4 | 44 | Sunday | 1
2025-11-03 | 2025 | November | 11 | 2025Q4 | 45 | Monday | 0
2025-11-04 | 2025 | November | 11 | 2025Q4 | 45 | Tuesday | 0
2025-11-05 | 2025 | November | 11 | 2025Q4 | 45 | Wednesday | 0
2025-11-06 | 2025 | November | 11 | 2025Q4 | 45 | Thursday | 0
2025-11-07 | 2025 | November | 11 | 2025Q4 | 45 | Friday | 0
2025-11-08 | 2025 | November | 11 | 2025Q4 | 45 | Saturday | 1
2025-11-09 | 2025 | November | 11 | 2025Q4 | 45 | Sunday | 1
2025-11-10 | 2025 | November | 11 | 2025Q4 | 46 | Monday | 0
2025-11-11 | 2025 | November | 11 | 2025Q4 | 46 | Tuesday | 0
2025-11-12 | 2025 | November | 11 | 2025Q4 | 46 | Wednesday | 0
2025-11-13 | 2025 | November | 11 | 2025Q4 | 46 | Thursday | 0
2025-11-14 | 2025 | November | 11 | 2025Q4 | 46 | Friday | 0
2025-11-15 | 2025 | November | 11 | 2025Q4 | 46 | Saturday | 1
2025-11-16 | 2025 | November | 11 | 2025Q4 | 46 | Sunday | 1
2025-11-17 | 2025 | November | 11 | 2025Q4 | 47 | Monday | 0
2025-11-18 | 2025 | November | 11 | 2025Q4 | 47 | Tuesday | 0
2025-11-19 | 2025 | November | 11 | 2025Q4 | 47 | Wednesday | 0
2025-11-20 | 2025 | November | 11 | 2025Q4 | 47 | Thursday | 0
2025-11-21 | 2025 | November | 11 | 2025Q4 | 47 | Friday | 0
2025-11-22 | 2025 | November | 11 | 2025Q4 | 47 | Saturday | 1
2025-11-23 | 2025 | November | 11 | 2025Q4 | 47 | Sunday | 1
2025-11-24 | 2025 | November | 11 | 2025Q4 | 48 | Monday | 0
2025-11-25 | 2025 | November | 11 | 2025Q4 | 48 | Tuesday | 0
2025-11-26 | 2025 | November | 11 | 2025Q4 | 48 | Wednesday | 0
2025-11-27 | 2025 | November | 11 | 2025Q4 | 48 | Thursday | 0
2025-11-28 | 2025 | November | 11 | 2025Q4 | 48 | Friday | 0
2025-11-29 | 2025 | November | 11 | 2025Q4 | 48 | Saturday | 1
2025-11-30 | 2025 | November | 11 | 2025Q4 | 48 | Sunday | 1
2025-12-01 | 2025 | December | 12 | 2025Q4 | 49 | Monday | 0
2025-12-02 | 2025 | December | 12 | 2025Q4 | 49 | Tuesday | 0
2025-12-03 | 2025 | December | 12 | 2025Q4 | 49 | Wednesday | 0
2025-12-04 | 2025 | December | 12 | 2025Q4 | 49 | Thursday | 0
2025-12-05 | 2025 | December | 12 | 2025Q4 | 49 | Friday | 0
2025-12-06 | 2025 | December | 12 | 2025Q4 | 49 | Saturday | 1
2025-12-07 | 2025 | December | 12 | 2025Q4 | 49 | Sunday | 1
2025-12-08 | 2025 | December | 12 | 2025Q4 | 50 | Monday | 0
2025-12-09 | 2025 | December | 12 | 2025Q4 | 50 | Tuesday | 0
2025-12-10 | 2025 | December | 12 | 2025Q4 | 50 | Wednesday | 0
2025-12-11 | 2025 | December | 12 | 2025Q4 | 50 | Thursday | 0
2025-12-12 | 2025 | December | 12 | 2025Q4 | 50 | Friday | 0
2025-12-13 | 2025 | December | 12 | 2025Q4 | 50 | Saturday | 1
2025-12-14 | 2025 | December | 12 | 2025Q4 | 50 | Sunday | 1
2025-12-15 | 2025 | December | 12 | 2025Q4 | 51 | Monday | 0
2025-12-16 | 2025 | December | 12 | 2025Q4 | 51 | Tuesday | 0
2025-12-17 | 2025 | December | 12 | 2025Q4 | 51 | Wednesday | 0
2025-12-18 | 2025 | December | 12 | 2025Q4 | 51 | Thursday | 0
2025-12-19 | 2025 | December | 12 | 2025Q4 | 51 | Friday | 0
2025-12-20 | 2025 | December | 12 | 2025Q4 | 51 | Saturday | 1
2025-12-21 | 2025 | December | 12 | 2025Q4 | 51 | Sunday | 1
2025-12-22 | 2025 | December | 12 | 2025Q4 | 52 | Monday | 0
2025-12-23 | 2025 | December | 12 | 2025Q4 | 52 | Tuesday | 0
2025-12-24 | 2025 | December | 12 | 2025Q4 | 52 | Wednesday | 0
2025-12-25 | 2025 | December | 12 | 2025Q4 | 52 | Thursday | 0
2025-12-26 | 2025 | December | 12 | 2025Q4 | 52 | Friday | 0
2025-12-27 | 2025 | December | 12 | 2025Q4 | 52 | Saturday | 1
2025-12-28 | 2025 | December | 12 | 2025Q4 | 52 | Sunday | 1
2025-12-29 | 2025 | December | 12 | 2025Q4 | 1 | Monday | 0
2025-12-30 | 2025 | December | 12 | 2025Q4 | 1 | Tuesday | 0
2025-12-31 | 2025 | December | 12 | 2025Q4 | 1 | Wednesday | 0
2026-01-01 | 2026 | January | 1 | 2026Q1 | 1 | Thursday | 0
2026-01-02 | 2026 | January | 1 | 2026Q1 | 1 | Friday | 0
2026-01-03 | 2026 | January | 1 | 2026Q1 | 1 | Saturday | 1
2026-01-04 | 2026 | January | 1 | 2026Q1 | 1 | Sunday | 1
2026-01-05 | 2026 | January | 1 | 2026Q1 | 2 | Monday | 0
2026-01-06 | 2026 | January | 1 | 2026Q1 | 2 | Tuesday | 0
2026-01-07 | 2026 | January | 1 | 2026Q1 | 2 | Wednesday | 0
2026-01-08 | 2026 | January | 1 | 2026Q1 | 2 | Thursday | 0
2026-01-09 | 2026 | January | 1 | 2026Q1 | 2 | Friday | 0
2026-01-10 | 2026 | January | 1 | 2026Q1 | 2 | Saturday | 1
2026-01-11 | 2026 | January | 1 | 2026Q1 | 2 | Sunday | 1
2026-01-12 | 2026 | January | 1 | 2026Q1 | 3 | Monday | 0
2026-01-13 | 2026 | January | 1 | 2026Q1 | 3 | Tuesday | 0
2026-01-14 | 2026 | January | 1 | 2026Q1 | 3 | Wednesday | 0
2026-01-15 | 2026 | January | 1 | 2026Q1 | 3 | Thursday | 0
2026-01-16 | 2026 | January | 1 | 2026Q1 | 3 | Friday | 0
2026-01-17 | 2026 | January | 1 | 2026Q1 | 3 | Saturday | 1
2026-01-18 | 2026 | January | 1 | 2026Q1 | 3 | Sunday | 1
2026-01-19 | 2026 | January | 1 | 2026Q1 | 4 | Monday | 0
2026-01-20 | 2026 | January | 1 | 2026Q1 | 4 | Tuesday | 0
2026-01-21 | 2026 | January | 1 | 2026Q1 | 4 | Wednesday | 0
2026-01-22 | 2026 | January | 1 | 2026Q1 | 4 | Thursday | 0
2026-01-23 | 2026 | January | 1 | 2026Q1 | 4 | Friday | 0
2026-01-24 | 2026 | January | 1 | 2026Q1 | 4 | Saturday | 1
2026-01-25 | 2026 | January | 1 | 2026Q1 | 4 | Sunday | 1
2026-01-26 | 2026 | January | 1 | 2026Q1 | 5 | Monday | 0
2026-01-27 | 2026 | January | 1 | 2026Q1 | 5 | Tuesday | 0
2026-01-28 | 2026 | January | 1 | 2026Q1 | 5 | Wednesday | 0
2026-01-29 | 2026 | January | 1 | 2026Q1 | 5 | Thursday | 0
2026-01-30 | 2026 | January | 1 | 2026Q1 | 5 | Friday | 0
2026-01-31 | 2026 | January | 1 | 2026Q1 | 5 | Saturday | 1
2026-02-01 | 2026 | February | 2 | 2026Q1 | 5 | Sunday | 1
2026-02-02 | 2026 | February | 2 | 2026Q1 | 6 | Monday | 0
2026-02-03 | 2026 | February | 2 | 2026Q1 | 6 | Tuesday | 0
2026-02-04 | 2026 | February | 2 | 2026Q1 | 6 | Wednesday | 0
2026-02-05 | 2026 | February | 2 | 2026Q1 | 6 | Thursday | 0
2026-02-06 | 2026 | February | 2 | 2026Q1 | 6 | Friday | 0
2026-02-07 | 2026 | February | 2 | 2026Q1 | 6 | Saturday | 1
2026-02-08 | 2026 | February | 2 | 2026Q1 | 6 | Sunday | 1
2026-02-09 | 2026 | February | 2 | 2026Q1 | 7 | Monday | 0
2026-02-10 | 2026 | February | 2 | 2026Q1 | 7 | Tuesday | 0
2026-02-11 | 2026 | February | 2 | 2026Q1 | 7 | Wednesday | 0
2026-02-12 | 2026 | February | 2 | 2026Q1 | 7 | Thursday | 0
2026-02-13 | 2026 | February | 2 | 2026Q1 | 7 | Friday | 0
2026-02-14 | 2026 | February | 2 | 2026Q1 | 7 | Saturday | 1
2026-02-15 | 2026 | February | 2 | 2026Q1 | 7 | Sunday | 1
2026-02-16 | 2026 | February | 2 | 2026Q1 | 8 | Monday | 0
2026-02-17 | 2026 | February | 2 | 2026Q1 | 8 | Tuesday | 0
2026-02-18 | 2026 | February | 2 | 2026Q1 | 8 | Wednesday | 0
2026-02-19 | 2026 | February | 2 | 2026Q1 | 8 | Thursday | 0
2026-02-20 | 2026 | February | 2 | 2026Q1 | 8 | Friday | 0
2026-02-21 | 2026 | February | 2 | 2026Q1 | 8 | Saturday | 1
2026-02-22 | 2026 | February | 2 | 2026Q1 | 8 | Sunday | 1
2026-02-23 | 2026 | February | 2 | 2026Q1 | 9 | Monday | 0
2026-02-24 | 2026 | February | 2 | 2026Q1 | 9 | Tuesday | 0
2026-02-25 | 2026 | February | 2 | 2026Q1 | 9 | Wednesday | 0
2026-02-26 | 2026 | February | 2 | 2026Q1 | 9 | Thursday | 0
2026-02-27 | 2026 | February | 2 | 2026Q1 | 9 | Friday | 0
2026-02-28 | 2026 | February | 2 | 2026Q1 | 9 | Saturday | 1
2026-03-01 | 2026 | March | 3 | 2026Q1 | 9 | Sunday | 1
2026-03-02 | 2026 | March | 3 | 2026Q1 | 10 | Monday | 0
2026-03-03 | 2026 | March | 3 | 2026Q1 | 10 | Tuesday | 0
2026-03-04 | 2026 | March | 3 | 2026Q1 | 10 | Wednesday | 0
2026-03-05 | 2026 | March | 3 | 2026Q1 | 10 | Thursday | 0
2026-03-06 | 2026 | March | 3 | 2026Q1 | 10 | Friday | 0
2026-03-07 | 2026 | March | 3 | 2026Q1 | 10 | Saturday | 1
2026-03-08 | 2026 | March | 3 | 2026Q1 | 10 | Sunday | 1
2026-03-09 | 2026 | March | 3 | 2026Q1 | 11 | Monday | 0
2026-03-10 | 2026 | March | 3 | 2026Q1 | 11 | Tuesday | 0
2026-03-11 | 2026 | March | 3 | 2026Q1 | 11 | Wednesday | 0
2026-03-12 | 2026 | March | 3 | 2026Q1 | 11 | Thursday | 0
2026-03-13 | 2026 | March | 3 | 2026Q1 | 11 | Friday | 0
2026-03-14 | 2026 | March | 3 | 2026Q1 | 11 | Saturday | 1
2026-03-15 | 2026 | March | 3 | 2026Q1 | 11 | Sunday | 1
2026-03-16 | 2026 | March | 3 | 2026Q1 | 12 | Monday | 0
2026-03-17 | 2026 | March | 3 | 2026Q1 | 12 | Tuesday | 0
2026-03-18 | 2026 | March | 3 | 2026Q1 | 12 | Wednesday | 0
2026-03-19 | 2026 | March | 3 | 2026Q1 | 12 | Thursday | 0
2026-03-20 | 2026 | March | 3 | 2026Q1 | 12 | Friday | 0
2026-03-21 | 2026 | March | 3 | 2026Q1 | 12 | Saturday | 1
2026-03-22 | 2026 | March | 3 | 2026Q1 | 12 | Sunday | 1
2026-03-23 | 2026 | March | 3 | 2026Q1 | 13 | Monday | 0
2026-03-24 | 2026 | March | 3 | 2026Q1 | 13 | Tuesday | 0
2026-03-25 | 2026 | March | 3 | 2026Q1 | 13 | Wednesday | 0
2026-03-26 | 2026 | March | 3 | 2026Q1 | 13 | Thursday | 0
2026-03-27 | 2026 | March | 3 | 2026Q1 | 13 | Friday | 0
2026-03-28 | 2026 | March | 3 | 2026Q1 | 13 | Saturday | 1
2026-03-29 | 2026 | March | 3 | 2026Q1 | 13 | Sunday | 1
2026-03-30 | 2026 | March | 3 | 2026Q1 | 14 | Monday | 0
2026-03-31 | 2026 | March | 3 | 2026Q1 | 14 | Tuesday | 0
2026-04-01 | 2026 | April | 4 | 2026Q2 | 14 | Wednesday | 0
2026-04-02 | 2026 | April | 4 | 2026Q2 | 14 | Thursday | 0
2026-04-03 | 2026 | April | 4 | 2026Q2 | 14 | Friday | 0
2026-04-04 | 2026 | April | 4 | 2026Q2 | 14 | Saturday | 1
2026-04-05 | 2026 | April | 4 | 2026Q2 | 14 | Sunday | 1
2026-04-06 | 2026 | April | 4 | 2026Q2 | 15 | Monday | 0
2026-04-07 | 2026 | April | 4 | 2026Q2 | 15 | Tuesday | 0
2026-04-08 | 2026 | April | 4 | 2026Q2 | 15 | Wednesday | 0
2026-04-09 | 2026 | April | 4 | 2026Q2 | 15 | Thursday | 0
2026-04-10 | 2026 | April | 4 | 2026Q2 | 15 | Friday | 0
2026-04-11 | 2026 | April | 4 | 2026Q2 | 15 | Saturday | 1
2026-04-12 | 2026 | April | 4 | 2026Q2 | 15 | Sunday | 1
2026-04-13 | 2026 | April | 4 | 2026Q2 | 16 | Monday | 0
2026-04-14 | 2026 | April | 4 | 2026Q2 | 16 | Tuesday | 0
2026-04-15 | 2026 | April | 4 | 2026Q2 | 16 | Wednesday | 0
2026-04-16 | 2026 | April | 4 | 2026Q2 | 16 | Thursday | 0
2026-04-17 | 2026 | April | 4 | 2026Q2 | 16 | Friday | 0
2026-04-18 | 2026 | April | 4 | 2026Q2 | 16 | Saturday | 1
2026-04-19 | 2026 | April | 4 | 2026Q2 | 16 | Sunday | 1
2026-04-20 | 2026 | April | 4 | 2026Q2 | 17 | Monday | 0
2026-04-21 | 2026 | April | 4 | 2026Q2 | 17 | Tuesday | 0
2026-04-22 | 2026 | April | 4 | 2026Q2 | 17 | Wednesday | 0
2026-04-23 | 2026 | April | 4 | 2026Q2 | 17 | Thursday | 0
2026-04-24 | 2026 | April | 4 | 2026Q2 | 17 | Friday | 0
2026-04-25 | 2026 | April | 4 | 2026Q2 | 17 | Saturday | 1
2026-04-26 | 2026 | April | 4 | 2026Q2 | 17 | Sunday | 1
2026-04-27 | 2026 | April | 4 | 2026Q2 | 18 | Monday | 0
2026-04-28 | 2026 | April | 4 | 2026Q2 | 18 | Tuesday | 0
2026-04-29 | 2026 | April | 4 | 2026Q2 | 18 | Wednesday | 0
2026-04-30 | 2026 | April | 4 | 2026Q2 | 18 | Thursday | 0
2026-05-01 | 2026 | May | 5 | 2026Q2 | 18 | Friday | 0
2026-05-02 | 2026 | May | 5 | 2026Q2 | 18 | Saturday | 1
2026-05-03 | 2026 | May | 5 | 2026Q2 | 18 | Sunday | 1
2026-05-04 | 2026 | May | 5 | 2026Q2 | 19 | Monday | 0
2026-05-05 | 2026 | May | 5 | 2026Q2 | 19 | Tuesday | 0
2026-05-06 | 2026 | May | 5 | 2026Q2 | 19 | Wednesday | 0
2026-05-07 | 2026 | May | 5 | 2026Q2 | 19 | Thursday | 0
2026-05-08 | 2026 | May | 5 | 2026Q2 | 19 | Friday | 0
2026-05-09 | 2026 | May | 5 | 2026Q2 | 19 | Saturday | 1
2026-05-10 | 2026 | May | 5 | 2026Q2 | 19 | Sunday | 1
2026-05-11 | 2026 | May | 5 | 2026Q2 | 20 | Monday | 0
2026-05-12 | 2026 | May | 5 | 2026Q2 | 20 | Tuesday | 0
2026-05-13 | 2026 | May | 5 | 2026Q2 | 20 | Wednesday | 0
2026-05-14 | 2026 | May | 5 | 2026Q2 | 20 | Thursday | 0
2026-05-15 | 2026 | May | 5 | 2026Q2 | 20 | Friday | 0
2026-05-16 | 2026 | May | 5 | 2026Q2 | 20 | Saturday | 1
2026-05-17 | 2026 | May | 5 | 2026Q2 | 20 | Sunday | 1
2026-05-18 | 2026 | May | 5 | 2026Q2 | 21 | Monday | 0
2026-05-19 | 2026 | May | 5 | 2026Q2 | 21 | Tuesday | 0
2026-05-20 | 2026 | May | 5 | 2026Q2 | 21 | Wednesday | 0
2026-05-21 | 2026 | May | 5 | 2026Q2 | 21 | Thursday | 0
2026-05-22 | 2026 | May | 5 | 2026Q2 | 21 | Friday | 0
2026-05-23 | 2026 | May | 5 | 2026Q2 | 21 | Saturday | 1
2026-05-24 | 2026 | May | 5 | 2026Q2 | 21 | Sunday | 1
2026-05-25 | 2026 | May | 5 | 2026Q2 | 22 | Monday | 0
2026-05-26 | 2026 | May | 5 | 2026Q2 | 22 | Tuesday | 0
2026-05-27 | 2026 | May | 5 | 2026Q2 | 22 | Wednesday | 0
2026-05-28 | 2026 | May | 5 | 2026Q2 | 22 | Thursday | 0
2026-05-29 | 2026 | May | 5 | 2026Q2 | 22 | Friday | 0
2026-05-30 | 2026 | May | 5 | 2026Q2 | 22 | Saturday | 1
2026-05-31 | 2026 | May | 5 | 2026Q2 | 22 | Sunday | 1
2026-06-01 | 2026 | June | 6 | 2026Q2 | 23 | Monday | 0
2026-06-02 | 2026 | June | 6 | 2026Q2 | 23 | Tuesday | 0
2026-06-03 | 2026 | June | 6 | 2026Q2 | 23 | Wednesday | 0
2026-06-04 | 2026 | June | 6 | 2026Q2 | 23 | Thursday | 0
2026-06-05 | 2026 | June | 6 | 2026Q2 | 23 | Friday | 0
2026-06-06 | 2026 | June | 6 | 2026Q2 | 23 | Saturday | 1
2026-06-07 | 2026 | June | 6 | 2026Q2 | 23 | Sunday | 1
2026-06-08 | 2026 | June | 6 | 2026Q2 | 24 | Monday | 0
2026-06-09 | 2026 | June | 6 | 2026Q2 | 24 | Tuesday | 0
2026-06-10 | 2026 | June | 6 | 2026Q2 | 24 | Wednesday | 0
2026-06-11 | 2026 | June | 6 | 2026Q2 | 24 | Thursday | 0
2026-06-12 | 2026 | June | 6 | 2026Q2 | 24 | Friday | 0
2026-06-13 | 2026 | June | 6 | 2026Q2 | 24 | Saturday | 1
2026-06-14 | 2026 | June | 6 | 2026Q2 | 24 | Sunday | 1
2026-06-15 | 2026 | June | 6 | 2026Q2 | 25 | Monday | 0
2026-06-16 | 2026 | June | 6 | 2026Q2 | 25 | Tuesday | 0
2026-06-17 | 2026 | June | 6 | 2026Q2 | 25 | Wednesday | 0
2026-06-18 | 2026 | June | 6 | 2026Q2 | 25 | Thursday | 0
2026-06-19 | 2026 | June | 6 | 2026Q2 | 25 | Friday | 0
2026-06-20 | 2026 | June | 6 | 2026Q2 | 25 | Saturday | 1
2026-06-21 | 2026 | June | 6 | 2026Q2 | 25 | Sunday | 1
2026-06-22 | 2026 | June | 6 | 2026Q2 | 26 | Monday | 0
2026-06-23 | 2026 | June | 6 | 2026Q2 | 26 | Tuesday | 0
2026-06-24 | 2026 | June | 6 | 2026Q2 | 26 | Wednesday | 0
2026-06-25 | 2026 | June | 6 | 2026Q2 | 26 | Thursday | 0
2026-06-26 | 2026 | June | 6 | 2026Q2 | 26 | Friday | 0
2026-06-27 | 2026 | June | 6 | 2026Q2 | 26 | Saturday | 1
2026-06-28 | 2026 | June | 6 | 2026Q2 | 26 | Sunday | 1
2026-06-29 | 2026 | June | 6 | 2026Q2 | 27 | Monday | 0
2026-06-30 | 2026 | June | 6 | 2026Q2 | 27 | Tuesday | 0
2026-07-01 | 2026 | July | 7 | 2026Q3 | 27 | Wednesday | 0
2026-07-02 | 2026 | July | 7 | 2026Q3 | 27 | Thursday | 0
2026-07-03 | 2026 | July | 7 | 2026Q3 | 27 | Friday | 0
2026-07-04 | 2026 | July | 7 | 2026Q3 | 27 | Saturday | 1
2026-07-05 | 2026 | July | 7 | 2026Q3 | 27 | Sunday | 1
2026-07-06 | 2026 | July | 7 | 2026Q3 | 28 | Monday | 0
2026-07-07 | 2026 | July | 7 | 2026Q3 | 28 | Tuesday | 0
2026-07-08 | 2026 | July | 7 | 2026Q3 | 28 | Wednesday | 0
2026-07-09 | 2026 | July | 7 | 2026Q3 | 28 | Thursday | 0
2026-07-10 | 2026 | July | 7 | 2026Q3 | 28 | Friday | 0
2026-07-11 | 2026 | July | 7 | 2026Q3 | 28 | Saturday | 1
2026-07-12 | 2026 | July | 7 | 2026Q3 | 28 | Sunday | 1
2026-07-13 | 2026 | July | 7 | 2026Q3 | 29 | Monday | 0
2026-07-14 | 2026 | July | 7 | 2026Q3 | 29 | Tuesday | 0
2026-07-15 | 2026 | July | 7 | 2026Q3 | 29 | Wednesday | 0
2026-07-16 | 2026 | July | 7 | 2026Q3 | 29 | Thursday | 0
2026-07-17 | 2026 | July | 7 | 2026Q3 | 29 | Friday | 0
2026-07-18 | 2026 | July | 7 | 2026Q3 | 29 | Saturday | 1
2026-07-19 | 2026 | July | 7 | 2026Q3 | 29 | Sunday | 1
2026-07-20 | 2026 | July | 7 | 2026Q3 | 30 | Monday | 0
2026-07-21 | 2026 | July | 7 | 2026Q3 | 30 | Tuesday | 0
2026-07-22 | 2026 | July | 7 | 2026Q3 | 30 | Wednesday | 0
2026-07-23 | 2026 | July | 7 | 2026Q3 | 30 | Thursday | 0
2026-07-24 | 2026 | July | 7 | 2026Q3 | 30 | Friday | 0
2026-07-25 | 2026 | July | 7 | 2026Q3 | 30 | Saturday | 1
2026-07-26 | 2026 | July | 7 | 2026Q3 | 30 | Sunday | 1
2026-07-27 | 2026 | July | 7 | 2026Q3 | 31 | Monday | 0
2026-07-28 | 2026 | July | 7 | 2026Q3 | 31 | Tuesday | 0
2026-07-29 | 2026 | July | 7 | 2026Q3 | 31 | Wednesday | 0
2026-07-30 | 2026 | July | 7 | 2026Q3 | 31 | Thursday | 0
2026-07-31 | 2026 | July | 7 | 2026Q3 | 31 | Friday | 0
2026-08-01 | 2026 | August | 8 | 2026Q3 | 31 | Saturday | 1
2026-08-02 | 2026 | August | 8 | 2026Q3 | 31 | Sunday | 1
2026-08-03 | 2026 | August | 8 | 2026Q3 | 32 | Monday | 0
2026-08-04 | 2026 | August | 8 | 2026Q3 | 32 | Tuesday | 0
2026-08-05 | 2026 | August | 8 | 2026Q3 | 32 | Wednesday | 0
2026-08-06 | 2026 | August | 8 | 2026Q3 | 32 | Thursday | 0
2026-08-07 | 2026 | August | 8 | 2026Q3 | 32 | Friday | 0
2026-08-08 | 2026 | August | 8 | 2026Q3 | 32 | Saturday | 1
2026-08-09 | 2026 | August | 8 | 2026Q3 | 32 | Sunday | 1
2026-08-10 | 2026 | August | 8 | 2026Q3 | 33 | Monday | 0
2026-08-11 | 2026 | August | 8 | 2026Q3 | 33 | Tuesday | 0
2026-08-12 | 2026 | August | 8 | 2026Q3 | 33 | Wednesday | 0
2026-08-13 | 2026 | August | 8 | 2026Q3 | 33 | Thursday | 0
2026-08-14 | 2026 | August | 8 | 2026Q3 | 33 | Friday | 0
2026-08-15 | 2026 | August | 8 | 2026Q3 | 33 | Saturday | 1
2026-08-16 | 2026 | August | 8 | 2026Q3 | 33 | Sunday | 1
2026-08-17 | 2026 | August | 8 | 2026Q3 | 34 | Monday | 0
2026-08-18 | 2026 | August | 8 | 2026Q3 | 34 | Tuesday | 0
2026-08-19 | 2026 | August | 8 | 2026Q3 | 34 | Wednesday | 0
2026-08-20 | 2026 | August | 8 | 2026Q3 | 34 | Thursday | 0
2026-08-21 | 2026 | August | 8 | 2026Q3 | 34 | Friday | 0
2026-08-22 | 2026 | August | 8 | 2026Q3 | 34 | Saturday | 1
2026-08-23 | 2026 | August | 8 | 2026Q3 | 34 | Sunday | 1
2026-08-24 | 2026 | August | 8 | 2026Q3 | 35 | Monday | 0
2026-08-25 | 2026 | August | 8 | 2026Q3 | 35 | Tuesday | 0
2026-08-26 | 2026 | August | 8 | 2026Q3 | 35 | Wednesday | 0
2026-08-27 | 2026 | August | 8 | 2026Q3 | 35 | Thursday | 0
2026-08-28 | 2026 | August | 8 | 2026Q3 | 35 | Friday | 0
2026-08-29 | 2026 | August | 8 | 2026Q3 | 35 | Saturday | 1
2026-08-30 | 2026 | August | 8 | 2026Q3 | 35 | Sunday | 1
2026-08-31 | 2026 | August | 8 | 2026Q3 | 36 | Monday | 0
2026-09-01 | 2026 | September | 9 | 2026Q3 | 36 | Tuesday | 0
2026-09-02 | 2026 | September | 9 | 2026Q3 | 36 | Wednesday | 0
2026-09-03 | 2026 | September | 9 | 2026Q3 | 36 | Thursday | 0
2026-09-04 | 2026 | September | 9 | 2026Q3 | 36 | Friday | 0
2026-09-05 | 2026 | September | 9 | 2026Q3 | 36 | Saturday | 1
2026-09-06 | 2026 | September | 9 | 2026Q3 | 36 | Sunday | 1
2026-09-07 | 2026 | September | 9 | 2026Q3 | 37 | Monday | 0
2026-09-08 | 2026 | September | 9 | 2026Q3 | 37 | Tuesday | 0
2026-09-09 | 2026 | September | 9 | 2026Q3 | 37 | Wednesday | 0
2026-09-10 | 2026 | September | 9 | 2026Q3 | 37 | Thursday | 0
2026-09-11 | 2026 | September | 9 | 2026Q3 | 37 | Friday | 0
2026-09-12 | 2026 | September | 9 | 2026Q3 | 37 | Saturday | 1
2026-09-13 | 2026 | September | 9 | 2026Q3 | 37 | Sunday | 1
2026-09-14 | 2026 | September | 9 | 2026Q3 | 38 | Monday | 0
2026-09-15 | 2026 | September | 9 | 2026Q3 | 38 | Tuesday | 0
2026-09-16 | 2026 | September | 9 | 2026Q3 | 38 | Wednesday | 0
2026-09-17 | 2026 | September | 9 | 2026Q3 | 38 | Thursday | 0
2026-09-18 | 2026 | September | 9 | 2026Q3 | 38 | Friday | 0
2026-09-19 | 2026 | September | 9 | 2026Q3 | 38 | Saturday | 1
2026-09-20 | 2026 | September | 9 | 2026Q3 | 38 | Sunday | 1
2026-09-21 | 2026 | September | 9 | 2026Q3 | 39 | Monday | 0
2026-09-22 | 2026 | September | 9 | 2026Q3 | 39 | Tuesday | 0
2026-09-23 | 2026 | September | 9 | 2026Q3 | 39 | Wednesday | 0
2026-09-24 | 2026 | September | 9 | 2026Q3 | 39 | Thursday | 0
2026-09-25 | 2026 | September | 9 | 2026Q3 | 39 | Friday | 0
2026-09-26 | 2026 | September | 9 | 2026Q3 | 39 | Saturday | 1
2026-09-27 | 2026 | September | 9 | 2026Q3 | 39 | Sunday | 1
2026-09-28 | 2026 | September | 9 | 2026Q3 | 40 | Monday | 0
2026-09-29 | 2026 | September | 9 | 2026Q3 | 40 | Tuesday | 0
2026-09-30 | 2026 | September | 9 | 2026Q3 | 40 | Wednesday | 0
2026-10-01 | 2026 | October | 10 | 2026Q4 | 40 | Thursday | 0
2026-10-02 | 2026 | October | 10 | 2026Q4 | 40 | Friday | 0
2026-10-03 | 2026 | October | 10 | 2026Q4 | 40 | Saturday | 1
2026-10-04 | 2026 | October | 10 | 2026Q4 | 40 | Sunday | 1
2026-10-05 | 2026 | October | 10 | 2026Q4 | 41 | Monday | 0
2026-10-06 | 2026 | October | 10 | 2026Q4 | 41 | Tuesday | 0
2026-10-07 | 2026 | October | 10 | 2026Q4 | 41 | Wednesday | 0
2026-10-08 | 2026 | October | 10 | 2026Q4 | 41 | Thursday | 0
2026-10-09 | 2026 | October | 10 | 2026Q4 | 41 | Friday | 0
2026-10-10 | 2026 | October | 10 | 2026Q4 | 41 | Saturday | 1
2026-10-11 | 2026 | October | 10 | 2026Q4 | 41 | Sunday | 1
2026-10-12 | 2026 | October | 10 | 2026Q4 | 42 | Monday | 0
2026-10-13 | 2026 | October | 10 | 2026Q4 | 42 | Tuesday | 0
2026-10-14 | 2026 | October | 10 | 2026Q4 | 42 | Wednesday | 0
2026-10-15 | 2026 | October | 10 | 2026Q4 | 42 | Thursday | 0
2026-10-16 | 2026 | October | 10 | 2026Q4 | 42 | Friday | 0
2026-10-17 | 2026 | October | 10 | 2026Q4 | 42 | Saturday | 1
2026-10-18 | 2026 | October | 10 | 2026Q4 | 42 | Sunday | 1
2026-10-19 | 2026 | October | 10 | 2026Q4 | 43 | Monday | 0
2026-10-20 | 2026 | October | 10 | 2026Q4 | 43 | Tuesday | 0
2026-10-21 | 2026 | October | 10 | 2026Q4 | 43 | Wednesday | 0
2026-10-22 | 2026 | October | 10 | 2026Q4 | 43 | Thursday | 0
2026-10-23 | 2026 | October | 10 | 2026Q4 | 43 | Friday | 0
2026-10-24 | 2026 | October | 10 | 2026Q4 | 43 | Saturday | 1
2026-10-25 | 2026 | October | 10 | 2026Q4 | 43 | Sunday | 1
2026-10-26 | 2026 | October | 10 | 2026Q4 | 44 | Monday | 0
2026-10-27 | 2026 | October | 10 | 2026Q4 | 44 | Tuesday | 0
2026-10-28 | 2026 | October | 10 | 2026Q4 | 44 | Wednesday | 0
2026-10-29 | 2026 | October | 10 | 2026Q4 | 44 | Thursday | 0
2026-10-30 | 2026 | October | 10 | 2026Q4 | 44 | Friday | 0
2026-10-31 | 2026 | October | 10 | 2026Q4 | 44 | Saturday | 1
2026-11-01 | 2026 | November | 11 | 2026Q4 | 44 | Sunday | 1
2026-11-02 | 2026 | November | 11 | 2026Q4 | 45 | Monday | 0
2026-11-03 | 2026 | November | 11 | 2026Q4 | 45 | Tuesday | 0
2026-11-04 | 2026 | November | 11 | 2026Q4 | 45 | Wednesday | 0
2026-11-05 | 2026 | November | 11 | 2026Q4 | 45 | Thursday | 0
2026-11-06 | 2026 | November | 11 | 2026Q4 | 45 | Friday | 0
2026-11-07 | 2026 | November | 11 | 2026Q4 | 45 | Saturday | 1
2026-11-08 | 2026 | November | 11 | 2026Q4 | 45 | Sunday | 1
2026-11-09 | 2026 | November | 11 | 2026Q4 | 46 | Monday | 0
2026-11-10 | 2026 | November | 11 | 2026Q4 | 46 | Tuesday | 0
2026-11-11 | 2026 | November | 11 | 2026Q4 | 46 | Wednesday | 0
2026-11-12 | 2026 | November | 11 | 2026Q4 | 46 | Thursday | 0
2026-11-13 | 2026 | November | 11 | 2026Q4 | 46 | Friday | 0
2026-11-14 | 2026 | November | 11 | 2026Q4 | 46 | Saturday | 1
2026-11-15 | 2026 | November | 11 | 2026Q4 | 46 | Sunday | 1
2026-11-16 | 2026 | November | 11 | 2026Q4 | 47 | Monday | 0
2026-11-17 | 2026 | November | 11 | 2026Q4 | 47 | Tuesday | 0
2026-11-18 | 2026 | November | 11 | 2026Q4 | 47 | Wednesday | 0
2026-11-19 | 2026 | November | 11 | 2026Q4 | 47 | Thursday | 0
2026-11-20 | 2026 | November | 11 | 2026Q4 | 47 | Friday | 0
2026-11-21 | 2026 | November | 11 | 2026Q4 | 47 | Saturday | 1
2026-11-22 | 2026 | November | 11 | 2026Q4 | 47 | Sunday | 1
2026-11-23 | 2026 | November | 11 | 2026Q4 | 48 | Monday | 0
2026-11-24 | 2026 | November | 11 | 2026Q4 | 48 | Tuesday | 0
2026-11-25 | 2026 | November | 11 | 2026Q4 | 48 | Wednesday | 0
2026-11-26 | 2026 | November | 11 | 2026Q4 | 48 | Thursday | 0
2026-11-27 | 2026 | November | 11 | 2026Q4 | 48 | Friday | 0
2026-11-28 | 2026 | November | 11 | 2026Q4 | 48 | Saturday | 1
2026-11-29 | 2026 | November | 11 | 2026Q4 | 48 | Sunday | 1
2026-11-30 | 2026 | November | 11 | 2026Q4 | 49 | Monday | 0
2026-12-01 | 2026 | December | 12 | 2026Q4 | 49 | Tuesday | 0
2026-12-02 | 2026 | December | 12 | 2026Q4 | 49 | Wednesday | 0
2026-12-03 | 2026 | December | 12 | 2026Q4 | 49 | Thursday | 0
2026-12-04 | 2026 | December | 12 | 2026Q4 | 49 | Friday | 0
2026-12-05 | 2026 | December | 12 | 2026Q4 | 49 | Saturday | 1
2026-12-06 | 2026 | December | 12 | 2026Q4 | 49 | Sunday | 1
2026-12-07 | 2026 | December | 12 | 2026Q4 | 50 | Monday | 0
2026-12-08 | 2026 | December | 12 | 2026Q4 | 50 | Tuesday | 0
2026-12-09 | 2026 | December | 12 | 2026Q4 | 50 | Wednesday | 0
2026-12-10 | 2026 | December | 12 | 2026Q4 | 50 | Thursday | 0
2026-12-11 | 2026 | December | 12 | 2026Q4 | 50 | Friday | 0
2026-12-12 | 2026 | December | 12 | 2026Q4 | 50 | Saturday | 1
2026-12-13 | 2026 | December | 12 | 2026Q4 | 50 | Sunday | 1
2026-12-14 | 2026 | December | 12 | 2026Q4 | 51 | Monday | 0
2026-12-15 | 2026 | December | 12 | 2026Q4 | 51 | Tuesday | 0
2026-12-16 | 2026 | December | 12 | 2026Q4 | 51 | Wednesday | 0
2026-12-17 | 2026 | December | 12 | 2026Q4 | 51 | Thursday | 0
2026-12-18 | 2026 | December | 12 | 2026Q4 | 51 | Friday | 0
2026-12-19 | 2026 | December | 12 | 2026Q4 | 51 | Saturday | 1
2026-12-20 | 2026 | December | 12 | 2026Q4 | 51 | Sunday | 1
2026-12-21 | 2026 | December | 12 | 2026Q4 | 52 | Monday | 0
2026-12-22 | 2026 | December | 12 | 2026Q4 | 52 | Tuesday | 0
2026-12-23 | 2026 | December | 12 | 2026Q4 | 52 | Wednesday | 0
2026-12-24 | 2026 | December | 12 | 2026Q4 | 52 | Thursday | 0
2026-12-25 | 2026 | December | 12 | 2026Q4 | 52 | Friday | 0
2026-12-26 | 2026 | December | 12 | 2026Q4 | 52 | Saturday | 1
2026-12-27 | 2026 | December | 12 | 2026Q4 | 52 | Sunday | 1
2026-12-28 | 2026 | December | 12 | 2026Q4 | 53 | Monday | 0
2026-12-29 | 2026 | December | 12 | 2026Q4 | 53 | Tuesday | 0
2026-12-30 | 2026 | December | 12 | 2026Q4 | 53 | Wednesday | 0
2026-12-31 | 2026 | December | 12 | 2026Q4 | 53 | Thursday | 0
2027-01-01 | 2027 | January | 1 | 2027Q1 | 53 | Friday | 0
2027-01-02 | 2027 | January | 1 | 2027Q1 | 53 | Saturday | 1
2027-01-03 | 2027 | January | 1 | 2027Q1 | 53 | Sunday | 1
2027-01-04 | 2027 | January | 1 | 2027Q1 | 1 | Monday | 0
2027-01-05 | 2027 | January | 1 | 2027Q1 | 1 | Tuesday | 0
2027-01-06 | 2027 | January | 1 | 2027Q1 | 1 | Wednesday | 0
2027-01-07 | 2027 | January | 1 | 2027Q1 | 1 | Thursday | 0
2027-01-08 | 2027 | January | 1 | 2027Q1 | 1 | Friday | 0
2027-01-09 | 2027 | January | 1 | 2027Q1 | 1 | Saturday | 1
2027-01-10 | 2027 | January | 1 | 2027Q1 | 1 | Sunday | 1
2027-01-11 | 2027 | January | 1 | 2027Q1 | 2 | Monday | 0
2027-01-12 | 2027 | January | 1 | 2027Q1 | 2 | Tuesday | 0
2027-01-13 | 2027 | January | 1 | 2027Q1 | 2 | Wednesday | 0
2027-01-14 | 2027 | January | 1 | 2027Q1 | 2 | Thursday | 0
2027-01-15 | 2027 | January | 1 | 2027Q1 | 2 | Friday | 0
2027-01-16 | 2027 | January | 1 | 2027Q1 | 2 | Saturday | 1
2027-01-17 | 2027 | January | 1 | 2027Q1 | 2 | Sunday | 1
2027-01-18 | 2027 | January | 1 | 2027Q1 | 3 | Monday | 0
2027-01-19 | 2027 | January | 1 | 2027Q1 | 3 | Tuesday | 0
2027-01-20 | 2027 | January | 1 | 2027Q1 | 3 | Wednesday | 0
2027-01-21 | 2027 | January | 1 | 2027Q1 | 3 | Thursday | 0
2027-01-22 | 2027 | January | 1 | 2027Q1 | 3 | Friday | 0
2027-01-23 | 2027 | January | 1 | 2027Q1 | 3 | Saturday | 1
2027-01-24 | 2027 | January | 1 | 2027Q1 | 3 | Sunday | 1
2027-01-25 | 2027 | January | 1 | 2027Q1 | 4 | Monday | 0
2027-01-26 | 2027 | January | 1 | 2027Q1 | 4 | Tuesday | 0
2027-01-27 | 2027 | January | 1 | 2027Q1 | 4 | Wednesday | 0
2027-01-28 | 2027 | January | 1 | 2027Q1 | 4 | Thursday | 0
2027-01-29 | 2027 | January | 1 | 2027Q1 | 4 | Friday | 0
2027-01-30 | 2027 | January | 1 | 2027Q1 | 4 | Saturday | 1
2027-01-31 | 2027 | January | 1 | 2027Q1 | 4 | Sunday | 1
2027-02-01 | 2027 | February | 2 | 2027Q1 | 5 | Monday | 0
2027-02-02 | 2027 | February | 2 | 2027Q1 | 5 | Tuesday | 0
2027-02-03 | 2027 | February | 2 | 2027Q1 | 5 | Wednesday | 0
2027-02-04 | 2027 | February | 2 | 2027Q1 | 5 | Thursday | 0
2027-02-05 | 2027 | February | 2 | 2027Q1 | 5 | Friday | 0
2027-02-06 | 2027 | February | 2 | 2027Q1 | 5 | Saturday | 1
2027-02-07 | 2027 | February | 2 | 2027Q1 | 5 | Sunday | 1
2027-02-08 | 2027 | February | 2 | 2027Q1 | 6 | Monday | 0
2027-02-09 | 2027 | February | 2 | 2027Q1 | 6 | Tuesday | 0
2027-02-10 | 2027 | February | 2 | 2027Q1 | 6 | Wednesday | 0
2027-02-11 | 2027 | February | 2 | 2027Q1 | 6 | Thursday | 0
2027-02-12 | 2027 | February | 2 | 2027Q1 | 6 | Friday | 0
2027-02-13 | 2027 | February | 2 | 2027Q1 | 6 | Saturday | 1
2027-02-14 | 2027 | February | 2 | 2027Q1 | 6 | Sunday | 1
2027-02-15 | 2027 | February | 2 | 2027Q1 | 7 | Monday | 0
2027-02-16 | 2027 | February | 2 | 2027Q1 | 7 | Tuesday | 0
2027-02-17 | 2027 | February | 2 | 2027Q1 | 7 | Wednesday | 0
2027-02-18 | 2027 | February | 2 | 2027Q1 | 7 | Thursday | 0
2027-02-19 | 2027 | February | 2 | 2027Q1 | 7 | Friday | 0
2027-02-20 | 2027 | February | 2 | 2027Q1 | 7 | Saturday | 1
2027-02-21 | 2027 | February | 2 | 2027Q1 | 7 | Sunday | 1
2027-02-22 | 2027 | February | 2 | 2027Q1 | 8 | Monday | 0
2027-02-23 | 2027 | February | 2 | 2027Q1 | 8 | Tuesday | 0
2027-02-24 | 2027 | February | 2 | 2027Q1 | 8 | Wednesday | 0
2027-02-25 | 2027 | February | 2 | 2027Q1 | 8 | Thursday | 0
2027-02-26 | 2027 | February | 2 | 2027Q1 | 8 | Friday | 0
2027-02-27 | 2027 | February | 2 | 2027Q1 | 8 | Saturday | 1
2027-02-28 | 2027 | February | 2 | 2027Q1 | 8 | Sunday | 1
2027-03-01 | 2027 | March | 3 | 2027Q1 | 9 | Monday | 0
2027-03-02 | 2027 | March | 3 | 2027Q1 | 9 | Tuesday | 0
2027-03-03 | 2027 | March | 3 | 2027Q1 | 9 | Wednesday | 0
2027-03-04 | 2027 | March | 3 | 2027Q1 | 9 | Thursday | 0
2027-03-05 | 2027 | March | 3 | 2027Q1 | 9 | Friday | 0
2027-03-06 | 2027 | March | 3 | 2027Q1 | 9 | Saturday | 1
2027-03-07 | 2027 | March | 3 | 2027Q1 | 9 | Sunday | 1
2027-03-08 | 2027 | March | 3 | 2027Q1 | 10 | Monday | 0
2027-03-09 | 2027 | March | 3 | 2027Q1 | 10 | Tuesday | 0
2027-03-10 | 2027 | March | 3 | 2027Q1 | 10 | Wednesday | 0
2027-03-11 | 2027 | March | 3 | 2027Q1 | 10 | Thursday | 0
2027-03-12 | 2027 | March | 3 | 2027Q1 | 10 | Friday | 0
2027-03-13 | 2027 | March | 3 | 2027Q1 | 10 | Saturday | 1
2027-03-14 | 2027 | March | 3 | 2027Q1 | 10 | Sunday | 1
2027-03-15 | 2027 | March | 3 | 2027Q1 | 11 | Monday | 0
2027-03-16 | 2027 | March | 3 | 2027Q1 | 11 | Tuesday | 0
2027-03-17 | 2027 | March | 3 | 2027Q1 | 11 | Wednesday | 0
2027-03-18 | 2027 | March | 3 | 2027Q1 | 11 | Thursday | 0
2027-03-19 | 2027 | March | 3 | 2027Q1 | 11 | Friday | 0
2027-03-20 | 2027 | March | 3 | 2027Q1 | 11 | Saturday | 1
2027-03-21 | 2027 | March | 3 | 2027Q1 | 11 | Sunday | 1
2027-03-22 | 2027 | March | 3 | 2027Q1 | 12 | Monday | 0
2027-03-23 | 2027 | March | 3 | 2027Q1 | 12 | Tuesday | 0
2027-03-24 | 2027 | March | 3 | 2027Q1 | 12 | Wednesday | 0
2027-03-25 | 2027 | March | 3 | 2027Q1 | 12 | Thursday | 0
2027-03-26 | 2027 | March | 3 | 2027Q1 | 12 | Friday | 0
2027-03-27 | 2027 | March | 3 | 2027Q1 | 12 | Saturday | 1
2027-03-28 | 2027 | March | 3 | 2027Q1 | 12 | Sunday | 1
2027-03-29 | 2027 | March | 3 | 2027Q1 | 13 | Monday | 0
2027-03-30 | 2027 | March | 3 | 2027Q1 | 13 | Tuesday | 0
2027-03-31 | 2027 | March | 3 | 2027Q1 | 13 | Wednesday | 0
2027-04-01 | 2027 | April | 4 | 2027Q2 | 13 | Thursday | 0
2027-04-02 | 2027 | April | 4 | 2027Q2 | 13 | Friday | 0
2027-04-03 | 2027 | April | 4 | 2027Q2 | 13 | Saturday | 1
2027-04-04 | 2027 | April | 4 | 2027Q2 | 13 | Sunday | 1
2027-04-05 | 2027 | April | 4 | 2027Q2 | 14 | Monday | 0
2027-04-06 | 2027 | April | 4 | 2027Q2 | 14 | Tuesday | 0
2027-04-07 | 2027 | April | 4 | 2027Q2 | 14 | Wednesday | 0
2027-04-08 | 2027 | April | 4 | 2027Q2 | 14 | Thursday | 0
2027-04-09 | 2027 | April | 4 | 2027Q2 | 14 | Friday | 0
2027-04-10 | 2027 | April | 4 | 2027Q2 | 14 | Saturday | 1
2027-04-11 | 2027 | April | 4 | 2027Q2 | 14 | Sunday | 1
2027-04-12 | 2027 | April | 4 | 2027Q2 | 15 | Monday | 0
2027-04-13 | 2027 | April | 4 | 2027Q2 | 15 | Tuesday | 0
2027-04-14 | 2027 | April | 4 | 2027Q2 | 15 | Wednesday | 0
2027-04-15 | 2027 | April | 4 | 2027Q2 | 15 | Thursday | 0
2027-04-16 | 2027 | April | 4 | 2027Q2 | 15 | Friday | 0
2027-04-17 | 2027 | April | 4 | 2027Q2 | 15 | Saturday | 1
2027-04-18 | 2027 | April | 4 | 2027Q2 | 15 | Sunday | 1
2027-04-19 | 2027 | April | 4 | 2027Q2 | 16 | Monday | 0
2027-04-20 | 2027 | April | 4 | 2027Q2 | 16 | Tuesday | 0
2027-04-21 | 2027 | April | 4 | 2027Q2 | 16 | Wednesday | 0
2027-04-22 | 2027 | April | 4 | 2027Q2 | 16 | Thursday | 0
2027-04-23 | 2027 | April | 4 | 2027Q2 | 16 | Friday | 0
2027-04-24 | 2027 | April | 4 | 2027Q2 | 16 | Saturday | 1
2027-04-25 | 2027 | April | 4 | 2027Q2 | 16 | Sunday | 1
2027-04-26 | 2027 | April | 4 | 2027Q2 | 17 | Monday | 0
2027-04-27 | 2027 | April | 4 | 2027Q2 | 17 | Tuesday | 0
2027-04-28 | 2027 | April | 4 | 2027Q2 | 17 | Wednesday | 0
2027-04-29 | 2027 | April | 4 | 2027Q2 | 17 | Thursday | 0
2027-04-30 | 2027 | April | 4 | 2027Q2 | 17 | Friday | 0
2027-05-01 | 2027 | May | 5 | 2027Q2 | 17 | Saturday | 1
2027-05-02 | 2027 | May | 5 | 2027Q2 | 17 | Sunday | 1
2027-05-03 | 2027 | May | 5 | 2027Q2 | 18 | Monday | 0
2027-05-04 | 2027 | May | 5 | 2027Q2 | 18 | Tuesday | 0
2027-05-05 | 2027 | May | 5 | 2027Q2 | 18 | Wednesday | 0
2027-05-06 | 2027 | May | 5 | 2027Q2 | 18 | Thursday | 0
2027-05-07 | 2027 | May | 5 | 2027Q2 | 18 | Friday | 0
2027-05-08 | 2027 | May | 5 | 2027Q2 | 18 | Saturday | 1
2027-05-09 | 2027 | May | 5 | 2027Q2 | 18 | Sunday | 1
2027-05-10 | 2027 | May | 5 | 2027Q2 | 19 | Monday | 0
2027-05-11 | 2027 | May | 5 | 2027Q2 | 19 | Tuesday | 0
2027-05-12 | 2027 | May | 5 | 2027Q2 | 19 | Wednesday | 0
2027-05-13 | 2027 | May | 5 | 2027Q2 | 19 | Thursday | 0
2027-05-14 | 2027 | May | 5 | 2027Q2 | 19 | Friday | 0
2027-05-15 | 2027 | May | 5 | 2027Q2 | 19 | Saturday | 1
2027-05-16 | 2027 | May | 5 | 2027Q2 | 19 | Sunday | 1
2027-05-17 | 2027 | May | 5 | 2027Q2 | 20 | Monday | 0
2027-05-18 | 2027 | May | 5 | 2027Q2 | 20 | Tuesday | 0
2027-05-19 | 2027 | May | 5 | 2027Q2 | 20 | Wednesday | 0
2027-05-20 | 2027 | May | 5 | 2027Q2 | 20 | Thursday | 0
2027-05-21 | 2027 | May | 5 | 2027Q2 | 20 | Friday | 0
2027-05-22 | 2027 | May | 5 | 2027Q2 | 20 | Saturday | 1
2027-05-23 | 2027 | May | 5 | 2027Q2 | 20 | Sunday | 1
2027-05-24 | 2027 | May | 5 | 2027Q2 | 21 | Monday | 0
2027-05-25 | 2027 | May | 5 | 2027Q2 | 21 | Tuesday | 0
2027-05-26 | 2027 | May | 5 | 2027Q2 | 21 | Wednesday | 0

## BridgeDependencies
TaskID | DependsOnTaskID
SYS-002 | SYS-001
CMP-002 | CMP-001
FIN-001 | CMP-002
FIN-002 | FIN-001
FIN-003 | FIN-002
FIN-004 | FIN-001
VAT-001 | FIN-001
VAT-002 | VAT-001
VAT-002 | FIN-003
BNK-001 | FIN-003
BNK-002 | BNK-001
SAL-001 | FIN-003
SAL-003 | SAL-001
SAL-004 | CMP-002
SAL-004 | FIN-003
PUR-001 | FIN-003
PUR-002 | CMP-002
PUR-002 | FIN-003
PUR-003 | SYS-003
INV-003 | INV-001
INV-004 | FIN-003
INV-004 | INV-001
INV-005 | INV-002
INV-005 | INV-004
INV-006 | INV-005
WH-001 | INV-001
PBI-002 | PBI-001
PBI-003 | PBI-002
MIG-001 | FIN-001
MIG-002 | MIG-001
MIG-003 | MIG-002
MIG-004 | FIN-003
MIG-004 | MIG-003
TST-002 | MIG-003
TST-003 | TST-002
GOL-001 | TST-003
GOL-002 | GOL-001
GOL-003 | GOL-002
PGL-001 | GOL-003

## Milestones
MilestoneID | Milestone | TargetDate | OwnerID | StatusID
MS-001 | Sandbox ready | 2026-05-19 | 8 | 2
MS-002 | Core setup complete | 2026-05-31 | 8 | 1
MS-003 | Master data imported | 2026-06-11 | 8 | 1
MS-004 | First dashboard draft | 2026-06-19 | 9 | 1
MS-005 | UAT sign-off | 2026-06-21 | 10 | 1
MS-006 | Go-live | 2026-06-29 | 1 | 1

## Measures_Catalogue
MeasureName | DAX | Description
Total Tasks | COUNTROWS(FactTasks) | Count of tasks
Completed Tasks | CALCULATE([Total Tasks], DimStatus[IsClosed] = 1) | Tasks with Done status
Open Tasks | [Total Tasks] - [Completed Tasks] | Remaining tasks
Completion % | DIVIDE([Completed Tasks],[Total Tasks]) | Overall completion
Avg Completion % | AVERAGE(FactTasks[CompletionPct]) | Average task completion
Overdue Tasks | CALCULATE([Total Tasks], FactTasks[DueDate] < TODAY() && DimStatus[IsClosed] = 0) | Tasks past due
Overdue % | DIVIDE([Overdue Tasks],[Total Tasks]) | Overdue share
Essentials Remaining | CALCULATE([Total Tasks], DimType[Type] = "Essential", DimStatus[IsClosed] = 0) | Open essential tasks
Risk High Tasks | CALCULATE([Total Tasks], FactTasks[Risk] = "High") | High risk tasks
Planned Effort (hrs) | SUM(FactTasks[EffortHoursEst]) | Estimated effort
Actual Effort (hrs) | SUM(FactTasks[EffortHoursActual]) | Actual effort
Effort Variance (hrs) | ['[Actual Effort (hrs)] - [Planned Effort (hrs)]'] | Variance

## PowerQuery_M
PowerQuery_M
let Source = Excel.Workbook(File.Contents(\"BC_Implementation_PowerBI_Pack.xlsx\"), null, true), FactTasks = Source{[Item=\"FactTasks\",Kind=\"Table\"]}[Data], DimModule = Source{[Item=\"DimModule\",Kind=\"Table\"]}[Data], DimOwner = Source{[Item=\"DimOwner\",Kind=\"Table\"]}[Data], DimPriority = Source{[Item=\"DimPriority\",Kind=\"Table\"]}[Data], DimType = Source{[Item=\"DimType\",Kind=\"Table\"]}[Data], DimStatus = Source{[Item=\"DimStatus\",Kind=\"Table\"]}[Data], DimDate = Source{[Item=\"DimDate\",Kind=\"Table\"]}[Data], BridgeDependencies = Source{[Item=\"BridgeDependencies\",Kind=\"Table\"]}[Data] in FactTasks

## Dashboard_Layout
PageOrder | PageName | Visuals
1 | Executive Summary | KPI cards (Total Tasks, Completion %, Overdue %), bar: tasks by status, bar: tasks by module, line: completion over time
2 | Finance | Matrix: tasks by phase/status, KPI: essentials remaining, bar: overdue tasks by owner
3 | Data Migration | Funnel: migration stages, table: defects, KPI: trial import completion
4 | Testing & UAT | KPI: open defects (use Notes), bar: tests by status, timeline: milestones
5 | Power BI | KPI: dashboard build progress, checklist table, RAG by page
6 | Risks & Issues | Table of high/blocked tasks, donut: risk split, bar: blocked by module