## FactTasks
CompanyID | CompanyTaskID | TaskID | TaskName | Description | ModuleID | PriorityID | TypeID | OwnerID | StatusID | Phase | StartDate | DueDate | CompletedDate | CompletionPct | EffortHoursEst | EffortHoursActual | Risk | Milestone | Notes
1 | SYS-001@1 | SYS-001 | Create users & permission sets | Define roles; assign permission sets; test access | 1 | 1 | 1 | 3 | 5 | Build | 2026-05-12 | 2026-05-19 | 2026-05-19 | 100 | 6 | 4 | Medium | Sandbox ready
1 | SYS-002@1 | SYS-002 | Configure email accounts | SMTP/Graph email; test document sending | 1 | 2 | 1 | 3 | 5 | Build | 2026-05-26 | 2026-05-29 | 2026-05-29 | 100 | 3 | 0 | Low
1 | SYS-003@1 | SYS-003 | Set up approval workflows (basic) | Approvals for purchase invoices and payments | 1 | 2 | 2 | 8 | 5 | Build | 2026-05-28 | 2026-06-05 | 2026-06-05 | 100 | 8 | 0 | Medium
1 | CMP-001@1 | CMP-001 | Company information | Address, VAT reg no, bank details, local settings | 2 | 1 | 1 | 8 | 5 | Build | 2026-05-05 | 2026-05-06 | 2026-05-06 | 100 | 2 | 2 | Low
1 | CMP-002@1 | CMP-002 | Number series | Customers, vendors, items, documents, journals | 2 | 1 | 1 | 8 | 5 | Build | 2026-05-07 | 2026-05-16 | 2026-05-16 | 100 | 6 | 4 | Medium
1 | FIN-001@1 | FIN-001 | Chart of Accounts review | Adopt UK COA or tailor; account categories | 3 | 1 | 1 | 2 | 5 | Build | 2026-05-08 | 2026-05-18 | 2026-05-18 | 100 | 12 | 10 | Medium
1 | FIN-003@1 | FIN-003 | General Posting Setup matrix | Map posting groups to GL accounts | 3 | 1 | 1 | 8 | 5 | Build | 2026-05-24 | 2026-05-31 | 2026-05-31 | 100 | 10 | 0 | High
1 | VAT-002@1 | VAT-002 | VAT Posting Setup matrix | 20% standard; accounts; VAT identifiers | 4 | 1 | 1 | 2 | 5 | Build | 2026-05-25 | 2026-06-01 | 2026-06-01 | 100 | 10 | 0 | High
1 | BNK-001@1 | BNK-001 | Bank accounts | Create bank accounts; posting groups; formats | 5 | 1 | 1 | 2 | 1 | Build | 2026-05-26 | 2026-06-02 |  | 0 | 6 | 0 | Medium
1 | SAL-004@1 | SAL-004 | Sales document setup | No. series; posting; shipment/invoice settings | 6 | 1 | 1 | 8 | 2 | Build | 2026-05-28 | 2026-06-04 |  | 50 | 8 | 0 | Medium
1 | PUR-002@1 | PUR-002 | Purchase document setup | No. series; posting; receipt/invoice settings | 7 | 1 | 1 | 8 | 2 | Build | 2026-05-28 | 2026-06-04 |  | 50 | 8 | 0 | Medium
1 | INV-001@1 | INV-001 | Inventory setup | Costing method (FIFO); inventory periods | 8 | 1 | 1 | 6 | 2 | Build | 2026-05-20 | 2026-05-25 |  | 70 | 6 | 4 | High
1 | INV-005@1 | INV-005 | Import item master | Import items; validate; pictures (optional) | 8 | 1 | 1 | 8 | 2 | Build | 2026-06-01 | 2026-06-11 |  | 50 | 12 | 0 | Medium | Master data imported
1 | MIG-003@1 | MIG-003 | Trial import #2 | Repeat import after fixes; validate posting | 14 | 1 | 1 | 8 | 2 | Build | 2026-06-01 | 2026-06-09 |  | 50 | 16 | 0 | Medium
1 | TST-003@1 | TST-003 | UAT | Business sign-off; training feedback | 15 | 1 | 1 | 10 | 1 | Test | 2026-06-07 | 2026-06-21 |  | 0 | 24 | 0 | High | UAT sign-off
1 | GOL-003@1 | GOL-003 | Go-live readiness review | Checklist: access, posting, VAT, reports | 16 | 1 | 1 | 1 | 1 | Deploy | 2026-06-23 | 2026-06-29 |  | 0 | 6 | 0 | High | Go-live
1 | PGL-001@1 | PGL-001 | Hypercare | Daily triage; defect fixes; adoption support | 17 | 1 | 1 | 1 | 1 | Optimise | 2026-06-30 | 2026-07-14 |  | 0 | 30 | 0 | Medium
1 | PBI-003@1 | PBI-003 | Build dashboard pages | Exec summary; Finance; Sales; Project; Risks | 13 | 1 | 1 | 9 | 1 | Build | 2026-06-05 | 2026-06-19 |  | 0 | 16 | 0 | Medium | First dashboard draft
2 | SYS-001@2 | SYS-001 | Create users & permission sets | Define roles; assign permission sets; test access | 1 | 1 | 1 | 3 | 2 | Build | 2026-06-11 | 2026-06-18 |  | 60 | 6 | 4 | Medium | Sandbox ready
2 | SYS-002@2 | SYS-002 | Configure email accounts | SMTP/Graph email; test document sending | 1 | 2 | 1 | 3 | 2 | Build | 2026-06-25 | 2026-06-28 |  | 50 | 3 | 0 | Low
2 | SYS-003@2 | SYS-003 | Set up approval workflows (basic) | Approvals for purchase invoices and payments | 1 | 2 | 2 | 8 | 2 | Build | 2026-06-27 | 2026-07-05 |  | 50 | 8 | 0 | Medium
2 | CMP-001@2 | CMP-001 | Company information | Address, VAT reg no, bank details, local settings | 2 | 1 | 1 | 8 | 2 | Build | 2026-06-04 | 2026-06-05 |  | 100 | 2 | 2 | Low
2 | CMP-002@2 | CMP-002 | Number series | Customers, vendors, items, documents, journals | 2 | 1 | 1 | 8 | 2 | Build | 2026-06-06 | 2026-06-15 |  | 70 | 6 | 4 | Medium
2 | FIN-001@2 | FIN-001 | Chart of Accounts review | Adopt UK COA or tailor; account categories | 3 | 1 | 1 | 2 | 2 | Build | 2026-06-07 | 2026-06-17 |  | 80 | 12 | 10 | Medium
2 | FIN-003@2 | FIN-003 | General Posting Setup matrix | Map posting groups to GL accounts | 3 | 1 | 1 | 8 | 2 | Build | 2026-06-23 | 2026-06-30 |  | 50 | 10 | 0 | High
2 | VAT-002@2 | VAT-002 | VAT Posting Setup matrix | 20% standard; accounts; VAT identifiers | 4 | 1 | 1 | 2 | 1 | Build | 2026-06-24 | 2026-07-01 |  | 0 | 10 | 0 | High
2 | BNK-001@2 | BNK-001 | Bank accounts | Create bank accounts; posting groups; formats | 5 | 1 | 1 | 2 | 1 | Build | 2026-06-25 | 2026-07-02 |  | 0 | 6 | 0 | Medium
2 | SAL-004@2 | SAL-004 | Sales document setup | No. series; posting; shipment/invoice settings | 6 | 1 | 1 | 8 | 1 | Build | 2026-06-27 | 2026-07-04 |  | 0 | 8 | 0 | Medium
2 | PUR-002@2 | PUR-002 | Purchase document setup | No. series; posting; receipt/invoice settings | 7 | 1 | 1 | 8 | 1 | Build | 2026-06-27 | 2026-07-04 |  | 0 | 8 | 0 | Medium
2 | INV-001@2 | INV-001 | Inventory setup | Costing method (FIFO); inventory periods | 8 | 1 | 1 | 6 | 2 | Build | 2026-06-19 | 2026-06-24 |  | 70 | 6 | 4 | High
2 | INV-005@2 | INV-005 | Import item master | Import items; validate; pictures (optional) | 8 | 1 | 1 | 8 | 1 | Build | 2026-07-01 | 2026-07-11 |  | 0 | 12 | 0 | Medium | Master data imported
2 | MIG-003@2 | MIG-003 | Trial import #2 | Repeat import after fixes; validate posting | 14 | 1 | 1 | 8 | 1 | Build | 2026-07-01 | 2026-07-09 |  | 0 | 16 | 0 | Medium
2 | TST-003@2 | TST-003 | UAT | Business sign-off; training feedback | 15 | 1 | 1 | 10 | 1 | Test | 2026-07-07 | 2026-07-21 |  | 0 | 24 | 0 | High | UAT sign-off
2 | GOL-003@2 | GOL-003 | Go-live readiness review | Checklist: access, posting, VAT, reports | 16 | 1 | 1 | 1 | 1 | Deploy | 2026-07-23 | 2026-07-29 |  | 0 | 6 | 0 | High | Go-live
2 | PGL-001@2 | PGL-001 | Hypercare | Daily triage; defect fixes; adoption support | 17 | 1 | 1 | 1 | 1 | Optimise | 2026-07-30 | 2026-08-13 |  | 0 | 30 | 0 | Medium
2 | PBI-003@2 | PBI-003 | Build dashboard pages | Exec summary; Finance; Sales; Project; Risks | 13 | 1 | 1 | 9 | 1 | Build | 2026-07-05 | 2026-07-19 |  | 0 | 16 | 0 | Medium | First dashboard draft
3 | SYS-001@3 | SYS-001 | Create users & permission sets | Define roles; assign permission sets; test access | 1 | 1 | 1 | 3 | 2 | Build | 2026-07-11 | 2026-07-18 |  | 60 | 6 | 4 | Medium | Sandbox ready
3 | SYS-002@3 | SYS-002 | Configure email accounts | SMTP/Graph email; test document sending | 1 | 2 | 1 | 3 | 1 | Build | 2026-07-25 | 2026-07-28 |  | 0 | 3 | 0 | Low
3 | SYS-003@3 | SYS-003 | Set up approval workflows (basic) | Approvals for purchase invoices and payments | 1 | 2 | 2 | 8 | 1 | Build | 2026-07-27 | 2026-08-04 |  | 0 | 8 | 0 | Medium
3 | CMP-001@3 | CMP-001 | Company information | Address, VAT reg no, bank details, local settings | 2 | 1 | 1 | 8 | 5 | Build | 2026-07-04 | 2026-07-05 | 2026-07-05 | 100 | 2 | 2 | Low
3 | CMP-002@3 | CMP-002 | Number series | Customers, vendors, items, documents, journals | 2 | 1 | 1 | 8 | 2 | Build | 2026-07-06 | 2026-07-15 |  | 70 | 6 | 4 | Medium
3 | FIN-001@3 | FIN-001 | Chart of Accounts review | Adopt UK COA or tailor; account categories | 3 | 1 | 1 | 2 | 3 | Build | 2026-07-07 | 2026-07-17 |  | 20 | 12 | 10 | High
3 | FIN-003@3 | FIN-003 | General Posting Setup matrix | Map posting groups to GL accounts | 3 | 1 | 1 | 8 | 3 | Build | 2026-07-23 | 2026-07-30 |  | 10 | 10 | 0 | High
3 | VAT-002@3 | VAT-002 | VAT Posting Setup matrix | 20% standard; accounts; VAT identifiers | 4 | 1 | 1 | 2 | 3 | Build | 2026-07-24 | 2026-07-31 |  | 10 | 10 | 0 | High
3 | BNK-001@3 | BNK-001 | Bank accounts | Create bank accounts; posting groups; formats | 5 | 1 | 1 | 2 | 1 | Build | 2026-07-25 | 2026-08-01 |  | 0 | 6 | 0 | Medium
3 | SAL-004@3 | SAL-004 | Sales document setup | No. series; posting; shipment/invoice settings | 6 | 1 | 1 | 8 | 1 | Build | 2026-07-27 | 2026-08-03 |  | 0 | 8 | 0 | Medium
3 | PUR-002@3 | PUR-002 | Purchase document setup | No. series; posting; receipt/invoice settings | 7 | 1 | 1 | 8 | 1 | Build | 2026-07-27 | 2026-08-03 |  | 0 | 8 | 0 | Medium
3 | INV-001@3 | INV-001 | Inventory setup | Costing method (FIFO); inventory periods | 8 | 1 | 1 | 6 | 2 | Build | 2026-07-19 | 2026-07-24 |  | 70 | 6 | 4 | High
3 | INV-005@3 | INV-005 | Import item master | Import items; validate; pictures (optional) | 8 | 1 | 1 | 8 | 1 | Build | 2026-07-31 | 2026-08-10 |  | 0 | 12 | 0 | Medium | Master data imported
3 | MIG-003@3 | MIG-003 | Trial import #2 | Repeat import after fixes; validate posting | 14 | 1 | 1 | 8 | 3 | Build | 2026-07-31 | 2026-08-08 |  | 10 | 16 | 0 | High
3 | TST-003@3 | TST-003 | UAT | Business sign-off; training feedback | 15 | 1 | 1 | 10 | 1 | Test | 2026-08-06 | 2026-08-20 |  | 0 | 24 | 0 | High | UAT sign-off
3 | GOL-003@3 | GOL-003 | Go-live readiness review | Checklist: access, posting, VAT, reports | 16 | 1 | 1 | 1 | 1 | Deploy | 2026-08-22 | 2026-08-28 |  | 0 | 6 | 0 | High | Go-live
3 | PGL-001@3 | PGL-001 | Hypercare | Daily triage; defect fixes; adoption support | 17 | 1 | 1 | 1 | 1 | Optimise | 2026-08-29 | 2026-09-12 |  | 0 | 30 | 0 | Medium
3 | PBI-003@3 | PBI-003 | Build dashboard pages | Exec summary; Finance; Sales; Project; Risks | 13 | 1 | 1 | 9 | 1 | Build | 2026-08-04 | 2026-08-18 |  | 0 | 16 | 0 | Medium | First dashboard draft

## DimCompany
CompanyID | Company | Industry | Country | VATProfile | BaseCurrency | DeploymentType | RAG | TargetGoLive
1 | Alpha Manufacturing Ltd | Manufacturing | UK | Standard (20%) | GBP | Pilot | Green | 2026-07-01
2 | Bravo Services Ltd | Professional Services | UK | Standard (20%) | GBP | Rollout | Amber | 2026-08-15
3 | Charlie Retail Ltd | Retail | UK | Standard (20%) | GBP | Rollout | Red | 2026-09-30

## DimModule
ModuleID | Module | ModuleSort
1 | System & Security | 1
2 | Company Setup | 2
3 | Finance - Core | 3
4 | VAT & Tax (UK) | 4
5 | Banking & Cash | 5
6 | Sales & Customer Centre | 6
7 | Purchasing | 7
8 | Inventory & Items | 8
9 | Warehouse | 9
10 | Human Resources | 10
11 | Fixed Assets | 11
12 | Projects/Jobs | 12
13 | Reporting & Power BI | 13
14 | Data Migration | 14
15 | Testing & UAT | 15
16 | Go-Live | 16
17 | Post-Go-Live | 17

## DimOwner
OwnerID | Owner | Function | Team
1 | Project Manager | PMO | Programme
2 | Finance Lead | Finance | Business
3 | IT Admin | IT | Technology
4 | Sales Admin | Sales | Business
5 | Purchasing Lead | Procurement | Business
6 | Inventory Lead | Operations | Business
7 | HR Admin | HR | Business
8 | BC Consultant | Partner | Delivery
9 | BI Analyst | BI | Technology
10 | Test Lead | QA | Delivery

## DimPriority
PriorityID | Priority | PrioritySort
1 | High | 1
2 | Medium | 2
3 | Low | 3

## DimType
TypeID | Type
1 | Essential
2 | Optional

## DimStatus
StatusID | Status | StatusSort | IsClosed
1 | Not Started | 1 | 0
2 | In Progress | 2 | 0
3 | Blocked | 3 | 0
4 | On Hold | 4 | 0
5 | Done | 5 | 1

## DimDate
Date | Year | Month | MonthName | Quarter | Week | DayName | IsWeekend
2025-05-26 | 2025 | 5 | May | 2025Q2 | 22 | Monday | 0
2025-05-27 | 2025 | 5 | May | 2025Q2 | 22 | Tuesday | 0
2025-05-28 | 2025 | 5 | May | 2025Q2 | 22 | Wednesday | 0
2025-05-29 | 2025 | 5 | May | 2025Q2 | 22 | Thursday | 0
2025-05-30 | 2025 | 5 | May | 2025Q2 | 22 | Friday | 0
2025-05-31 | 2025 | 5 | May | 2025Q2 | 22 | Saturday | 1
2025-06-01 | 2025 | 6 | June | 2025Q2 | 22 | Sunday | 1
2025-06-02 | 2025 | 6 | June | 2025Q2 | 23 | Monday | 0
2025-06-03 | 2025 | 6 | June | 2025Q2 | 23 | Tuesday | 0
2025-06-04 | 2025 | 6 | June | 2025Q2 | 23 | Wednesday | 0
2025-06-05 | 2025 | 6 | June | 2025Q2 | 23 | Thursday | 0
2025-06-06 | 2025 | 6 | June | 2025Q2 | 23 | Friday | 0
2025-06-07 | 2025 | 6 | June | 2025Q2 | 23 | Saturday | 1
2025-06-08 | 2025 | 6 | June | 2025Q2 | 23 | Sunday | 1
2025-06-09 | 2025 | 6 | June | 2025Q2 | 24 | Monday | 0
2025-06-10 | 2025 | 6 | June | 2025Q2 | 24 | Tuesday | 0
2025-06-11 | 2025 | 6 | June | 2025Q2 | 24 | Wednesday | 0
2025-06-12 | 2025 | 6 | June | 2025Q2 | 24 | Thursday | 0
2025-06-13 | 2025 | 6 | June | 2025Q2 | 24 | Friday | 0
2025-06-14 | 2025 | 6 | June | 2025Q2 | 24 | Saturday | 1
2025-06-15 | 2025 | 6 | June | 2025Q2 | 24 | Sunday | 1
2025-06-16 | 2025 | 6 | June | 2025Q2 | 25 | Monday | 0
2025-06-17 | 2025 | 6 | June | 2025Q2 | 25 | Tuesday | 0
2025-06-18 | 2025 | 6 | June | 2025Q2 | 25 | Wednesday | 0
2025-06-19 | 2025 | 6 | June | 2025Q2 | 25 | Thursday | 0
2025-06-20 | 2025 | 6 | June | 2025Q2 | 25 | Friday | 0
2025-06-21 | 2025 | 6 | June | 2025Q2 | 25 | Saturday | 1
2025-06-22 | 2025 | 6 | June | 2025Q2 | 25 | Sunday | 1
2025-06-23 | 2025 | 6 | June | 2025Q2 | 26 | Monday | 0
2025-06-24 | 2025 | 6 | June | 2025Q2 | 26 | Tuesday | 0
2025-06-25 | 2025 | 6 | June | 2025Q2 | 26 | Wednesday | 0
2025-06-26 | 2025 | 6 | June | 2025Q2 | 26 | Thursday | 0
2025-06-27 | 2025 | 6 | June | 2025Q2 | 26 | Friday | 0
2025-06-28 | 2025 | 6 | June | 2025Q2 | 26 | Saturday | 1
2025-06-29 | 2025 | 6 | June | 2025Q2 | 26 | Sunday | 1
2025-06-30 | 2025 | 6 | June | 2025Q2 | 27 | Monday | 0
2025-07-01 | 2025 | 7 | July | 2025Q3 | 27 | Tuesday | 0
2025-07-02 | 2025 | 7 | July | 2025Q3 | 27 | Wednesday | 0
2025-07-03 | 2025 | 7 | July | 2025Q3 | 27 | Thursday | 0
2025-07-04 | 2025 | 7 | July | 2025Q3 | 27 | Friday | 0
2025-07-05 | 2025 | 7 | July | 2025Q3 | 27 | Saturday | 1
2025-07-06 | 2025 | 7 | July | 2025Q3 | 27 | Sunday | 1
2025-07-07 | 2025 | 7 | July | 2025Q3 | 28 | Monday | 0
2025-07-08 | 2025 | 7 | July | 2025Q3 | 28 | Tuesday | 0
2025-07-09 | 2025 | 7 | July | 2025Q3 | 28 | Wednesday | 0
2025-07-10 | 2025 | 7 | July | 2025Q3 | 28 | Thursday | 0
2025-07-11 | 2025 | 7 | July | 2025Q3 | 28 | Friday | 0
2025-07-12 | 2025 | 7 | July | 2025Q3 | 28 | Saturday | 1
2025-07-13 | 2025 | 7 | July | 2025Q3 | 28 | Sunday | 1
2025-07-14 | 2025 | 7 | July | 2025Q3 | 29 | Monday | 0
2025-07-15 | 2025 | 7 | July | 2025Q3 | 29 | Tuesday | 0
2025-07-16 | 2025 | 7 | July | 2025Q3 | 29 | Wednesday | 0
2025-07-17 | 2025 | 7 | July | 2025Q3 | 29 | Thursday | 0
2025-07-18 | 2025 | 7 | July | 2025Q3 | 29 | Friday | 0
2025-07-19 | 2025 | 7 | July | 2025Q3 | 29 | Saturday | 1
2025-07-20 | 2025 | 7 | July | 2025Q3 | 29 | Sunday | 1
2025-07-21 | 2025 | 7 | July | 2025Q3 | 30 | Monday | 0
2025-07-22 | 2025 | 7 | July | 2025Q3 | 30 | Tuesday | 0
2025-07-23 | 2025 | 7 | July | 2025Q3 | 30 | Wednesday | 0
2025-07-24 | 2025 | 7 | July | 2025Q3 | 30 | Thursday | 0
2025-07-25 | 2025 | 7 | July | 2025Q3 | 30 | Friday | 0
2025-07-26 | 2025 | 7 | July | 2025Q3 | 30 | Saturday | 1
2025-07-27 | 2025 | 7 | July | 2025Q3 | 30 | Sunday | 1
2025-07-28 | 2025 | 7 | July | 2025Q3 | 31 | Monday | 0
2025-07-29 | 2025 | 7 | July | 2025Q3 | 31 | Tuesday | 0
2025-07-30 | 2025 | 7 | July | 2025Q3 | 31 | Wednesday | 0
2025-07-31 | 2025 | 7 | July | 2025Q3 | 31 | Thursday | 0
2025-08-01 | 2025 | 8 | August | 2025Q3 | 31 | Friday | 0
2025-08-02 | 2025 | 8 | August | 2025Q3 | 31 | Saturday | 1
2025-08-03 | 2025 | 8 | August | 2025Q3 | 31 | Sunday | 1
2025-08-04 | 2025 | 8 | August | 2025Q3 | 32 | Monday | 0
2025-08-05 | 2025 | 8 | August | 2025Q3 | 32 | Tuesday | 0
2025-08-06 | 2025 | 8 | August | 2025Q3 | 32 | Wednesday | 0
2025-08-07 | 2025 | 8 | August | 2025Q3 | 32 | Thursday | 0
2025-08-08 | 2025 | 8 | August | 2025Q3 | 32 | Friday | 0
2025-08-09 | 2025 | 8 | August | 2025Q3 | 32 | Saturday | 1
2025-08-10 | 2025 | 8 | August | 2025Q3 | 32 | Sunday | 1
2025-08-11 | 2025 | 8 | August | 2025Q3 | 33 | Monday | 0
2025-08-12 | 2025 | 8 | August | 2025Q3 | 33 | Tuesday | 0
2025-08-13 | 2025 | 8 | August | 2025Q3 | 33 | Wednesday | 0
2025-08-14 | 2025 | 8 | August | 2025Q3 | 33 | Thursday | 0
2025-08-15 | 2025 | 8 | August | 2025Q3 | 33 | Friday | 0
2025-08-16 | 2025 | 8 | August | 2025Q3 | 33 | Saturday | 1
2025-08-17 | 2025 | 8 | August | 2025Q3 | 33 | Sunday | 1
2025-08-18 | 2025 | 8 | August | 2025Q3 | 34 | Monday | 0
2025-08-19 | 2025 | 8 | August | 2025Q3 | 34 | Tuesday | 0
2025-08-20 | 2025 | 8 | August | 2025Q3 | 34 | Wednesday | 0
2025-08-21 | 2025 | 8 | August | 2025Q3 | 34 | Thursday | 0
2025-08-22 | 2025 | 8 | August | 2025Q3 | 34 | Friday | 0
2025-08-23 | 2025 | 8 | August | 2025Q3 | 34 | Saturday | 1
2025-08-24 | 2025 | 8 | August | 2025Q3 | 34 | Sunday | 1
2025-08-25 | 2025 | 8 | August | 2025Q3 | 35 | Monday | 0
2025-08-26 | 2025 | 8 | August | 2025Q3 | 35 | Tuesday | 0
2025-08-27 | 2025 | 8 | August | 2025Q3 | 35 | Wednesday | 0
2025-08-28 | 2025 | 8 | August | 2025Q3 | 35 | Thursday | 0
2025-08-29 | 2025 | 8 | August | 2025Q3 | 35 | Friday | 0
2025-08-30 | 2025 | 8 | August | 2025Q3 | 35 | Saturday | 1
2025-08-31 | 2025 | 8 | August | 2025Q3 | 35 | Sunday | 1
2025-09-01 | 2025 | 9 | September | 2025Q3 | 36 | Monday | 0
2025-09-02 | 2025 | 9 | September | 2025Q3 | 36 | Tuesday | 0
2025-09-03 | 2025 | 9 | September | 2025Q3 | 36 | Wednesday | 0
2025-09-04 | 2025 | 9 | September | 2025Q3 | 36 | Thursday | 0
2025-09-05 | 2025 | 9 | September | 2025Q3 | 36 | Friday | 0
2025-09-06 | 2025 | 9 | September | 2025Q3 | 36 | Saturday | 1
2025-09-07 | 2025 | 9 | September | 2025Q3 | 36 | Sunday | 1
2025-09-08 | 2025 | 9 | September | 2025Q3 | 37 | Monday | 0
2025-09-09 | 2025 | 9 | September | 2025Q3 | 37 | Tuesday | 0
2025-09-10 | 2025 | 9 | September | 2025Q3 | 37 | Wednesday | 0
2025-09-11 | 2025 | 9 | September | 2025Q3 | 37 | Thursday | 0
2025-09-12 | 2025 | 9 | September | 2025Q3 | 37 | Friday | 0
2025-09-13 | 2025 | 9 | September | 2025Q3 | 37 | Saturday | 1
2025-09-14 | 2025 | 9 | September | 2025Q3 | 37 | Sunday | 1
2025-09-15 | 2025 | 9 | September | 2025Q3 | 38 | Monday | 0
2025-09-16 | 2025 | 9 | September | 2025Q3 | 38 | Tuesday | 0
2025-09-17 | 2025 | 9 | September | 2025Q3 | 38 | Wednesday | 0
2025-09-18 | 2025 | 9 | September | 2025Q3 | 38 | Thursday | 0
2025-09-19 | 2025 | 9 | September | 2025Q3 | 38 | Friday | 0
2025-09-20 | 2025 | 9 | September | 2025Q3 | 38 | Saturday | 1
2025-09-21 | 2025 | 9 | September | 2025Q3 | 38 | Sunday | 1
2025-09-22 | 2025 | 9 | September | 2025Q3 | 39 | Monday | 0
2025-09-23 | 2025 | 9 | September | 2025Q3 | 39 | Tuesday | 0
2025-09-24 | 2025 | 9 | September | 2025Q3 | 39 | Wednesday | 0
2025-09-25 | 2025 | 9 | September | 2025Q3 | 39 | Thursday | 0
2025-09-26 | 2025 | 9 | September | 2025Q3 | 39 | Friday | 0
2025-09-27 | 2025 | 9 | September | 2025Q3 | 39 | Saturday | 1
2025-09-28 | 2025 | 9 | September | 2025Q3 | 39 | Sunday | 1
2025-09-29 | 2025 | 9 | September | 2025Q3 | 40 | Monday | 0
2025-09-30 | 2025 | 9 | September | 2025Q3 | 40 | Tuesday | 0
2025-10-01 | 2025 | 10 | October | 2025Q4 | 40 | Wednesday | 0
2025-10-02 | 2025 | 10 | October | 2025Q4 | 40 | Thursday | 0
2025-10-03 | 2025 | 10 | October | 2025Q4 | 40 | Friday | 0
2025-10-04 | 2025 | 10 | October | 2025Q4 | 40 | Saturday | 1
2025-10-05 | 2025 | 10 | October | 2025Q4 | 40 | Sunday | 1
2025-10-06 | 2025 | 10 | October | 2025Q4 | 41 | Monday | 0
2025-10-07 | 2025 | 10 | October | 2025Q4 | 41 | Tuesday | 0
2025-10-08 | 2025 | 10 | October | 2025Q4 | 41 | Wednesday | 0
2025-10-09 | 2025 | 10 | October | 2025Q4 | 41 | Thursday | 0
2025-10-10 | 2025 | 10 | October | 2025Q4 | 41 | Friday | 0
2025-10-11 | 2025 | 10 | October | 2025Q4 | 41 | Saturday | 1
2025-10-12 | 2025 | 10 | October | 2025Q4 | 41 | Sunday | 1
2025-10-13 | 2025 | 10 | October | 2025Q4 | 42 | Monday | 0
2025-10-14 | 2025 | 10 | October | 2025Q4 | 42 | Tuesday | 0
2025-10-15 | 2025 | 10 | October | 2025Q4 | 42 | Wednesday | 0
2025-10-16 | 2025 | 10 | October | 2025Q4 | 42 | Thursday | 0
2025-10-17 | 2025 | 10 | October | 2025Q4 | 42 | Friday | 0
2025-10-18 | 2025 | 10 | October | 2025Q4 | 42 | Saturday | 1
2025-10-19 | 2025 | 10 | October | 2025Q4 | 42 | Sunday | 1
2025-10-20 | 2025 | 10 | October | 2025Q4 | 43 | Monday | 0
2025-10-21 | 2025 | 10 | October | 2025Q4 | 43 | Tuesday | 0
2025-10-22 | 2025 | 10 | October | 2025Q4 | 43 | Wednesday | 0
2025-10-23 | 2025 | 10 | October | 2025Q4 | 43 | Thursday | 0
2025-10-24 | 2025 | 10 | October | 2025Q4 | 43 | Friday | 0
2025-10-25 | 2025 | 10 | October | 2025Q4 | 43 | Saturday | 1
2025-10-26 | 2025 | 10 | October | 2025Q4 | 43 | Sunday | 1
2025-10-27 | 2025 | 10 | October | 2025Q4 | 44 | Monday | 0
2025-10-28 | 2025 | 10 | October | 2025Q4 | 44 | Tuesday | 0
2025-10-29 | 2025 | 10 | October | 2025Q4 | 44 | Wednesday | 0
2025-10-30 | 2025 | 10 | October | 2025Q4 | 44 | Thursday | 0
2025-10-31 | 2025 | 10 | October | 2025Q4 | 44 | Friday | 0
2025-11-01 | 2025 | 11 | November | 2025Q4 | 44 | Saturday | 1
2025-11-02 | 2025 | 11 | November | 2025Q4 | 44 | Sunday | 1
2025-11-03 | 2025 | 11 | November | 2025Q4 | 45 | Monday | 0
2025-11-04 | 2025 | 11 | November | 2025Q4 | 45 | Tuesday | 0
2025-11-05 | 2025 | 11 | November | 2025Q4 | 45 | Wednesday | 0
2025-11-06 | 2025 | 11 | November | 2025Q4 | 45 | Thursday | 0
2025-11-07 | 2025 | 11 | November | 2025Q4 | 45 | Friday | 0
2025-11-08 | 2025 | 11 | November | 2025Q4 | 45 | Saturday | 1
2025-11-09 | 2025 | 11 | November | 2025Q4 | 45 | Sunday | 1
2025-11-10 | 2025 | 11 | November | 2025Q4 | 46 | Monday | 0
2025-11-11 | 2025 | 11 | November | 2025Q4 | 46 | Tuesday | 0
2025-11-12 | 2025 | 11 | November | 2025Q4 | 46 | Wednesday | 0
2025-11-13 | 2025 | 11 | November | 2025Q4 | 46 | Thursday | 0
2025-11-14 | 2025 | 11 | November | 2025Q4 | 46 | Friday | 0
2025-11-15 | 2025 | 11 | November | 2025Q4 | 46 | Saturday | 1
2025-11-16 | 2025 | 11 | November | 2025Q4 | 46 | Sunday | 1
2025-11-17 | 2025 | 11 | November | 2025Q4 | 47 | Monday | 0
2025-11-18 | 2025 | 11 | November | 2025Q4 | 47 | Tuesday | 0
2025-11-19 | 2025 | 11 | November | 2025Q4 | 47 | Wednesday | 0
2025-11-20 | 2025 | 11 | November | 2025Q4 | 47 | Thursday | 0
2025-11-21 | 2025 | 11 | November | 2025Q4 | 47 | Friday | 0
2025-11-22 | 2025 | 11 | November | 2025Q4 | 47 | Saturday | 1
2025-11-23 | 2025 | 11 | November | 2025Q4 | 47 | Sunday | 1
2025-11-24 | 2025 | 11 | November | 2025Q4 | 48 | Monday | 0
2025-11-25 | 2025 | 11 | November | 2025Q4 | 48 | Tuesday | 0
2025-11-26 | 2025 | 11 | November | 2025Q4 | 48 | Wednesday | 0
2025-11-27 | 2025 | 11 | November | 2025Q4 | 48 | Thursday | 0
2025-11-28 | 2025 | 11 | November | 2025Q4 | 48 | Friday | 0
2025-11-29 | 2025 | 11 | November | 2025Q4 | 48 | Saturday | 1
2025-11-30 | 2025 | 11 | November | 2025Q4 | 48 | Sunday | 1
2025-12-01 | 2025 | 12 | December | 2025Q4 | 49 | Monday | 0
2025-12-02 | 2025 | 12 | December | 2025Q4 | 49 | Tuesday | 0
2025-12-03 | 2025 | 12 | December | 2025Q4 | 49 | Wednesday | 0
2025-12-04 | 2025 | 12 | December | 2025Q4 | 49 | Thursday | 0
2025-12-05 | 2025 | 12 | December | 2025Q4 | 49 | Friday | 0
2025-12-06 | 2025 | 12 | December | 2025Q4 | 49 | Saturday | 1
2025-12-07 | 2025 | 12 | December | 2025Q4 | 49 | Sunday | 1
2025-12-08 | 2025 | 12 | December | 2025Q4 | 50 | Monday | 0
2025-12-09 | 2025 | 12 | December | 2025Q4 | 50 | Tuesday | 0
2025-12-10 | 2025 | 12 | December | 2025Q4 | 50 | Wednesday | 0
2025-12-11 | 2025 | 12 | December | 2025Q4 | 50 | Thursday | 0
2025-12-12 | 2025 | 12 | December | 2025Q4 | 50 | Friday | 0
2025-12-13 | 2025 | 12 | December | 2025Q4 | 50 | Saturday | 1
2025-12-14 | 2025 | 12 | December | 2025Q4 | 50 | Sunday | 1
2025-12-15 | 2025 | 12 | December | 2025Q4 | 51 | Monday | 0
2025-12-16 | 2025 | 12 | December | 2025Q4 | 51 | Tuesday | 0
2025-12-17 | 2025 | 12 | December | 2025Q4 | 51 | Wednesday | 0
2025-12-18 | 2025 | 12 | December | 2025Q4 | 51 | Thursday | 0
2025-12-19 | 2025 | 12 | December | 2025Q4 | 51 | Friday | 0
2025-12-20 | 2025 | 12 | December | 2025Q4 | 51 | Saturday | 1
2025-12-21 | 2025 | 12 | December | 2025Q4 | 51 | Sunday | 1
2025-12-22 | 2025 | 12 | December | 2025Q4 | 52 | Monday | 0
2025-12-23 | 2025 | 12 | December | 2025Q4 | 52 | Tuesday | 0
2025-12-24 | 2025 | 12 | December | 2025Q4 | 52 | Wednesday | 0
2025-12-25 | 2025 | 12 | December | 2025Q4 | 52 | Thursday | 0
2025-12-26 | 2025 | 12 | December | 2025Q4 | 52 | Friday | 0
2025-12-27 | 2025 | 12 | December | 2025Q4 | 52 | Saturday | 1
2025-12-28 | 2025 | 12 | December | 2025Q4 | 52 | Sunday | 1
2025-12-29 | 2025 | 12 | December | 2025Q4 | 1 | Monday | 0
2025-12-30 | 2025 | 12 | December | 2025Q4 | 1 | Tuesday | 0
2025-12-31 | 2025 | 12 | December | 2025Q4 | 1 | Wednesday | 0
2026-01-01 | 2026 | 1 | January | 2026Q1 | 1 | Thursday | 0
2026-01-02 | 2026 | 1 | January | 2026Q1 | 1 | Friday | 0
2026-01-03 | 2026 | 1 | January | 2026Q1 | 1 | Saturday | 1
2026-01-04 | 2026 | 1 | January | 2026Q1 | 1 | Sunday | 1
2026-01-05 | 2026 | 1 | January | 2026Q1 | 2 | Monday | 0
2026-01-06 | 2026 | 1 | January | 2026Q1 | 2 | Tuesday | 0
2026-01-07 | 2026 | 1 | January | 2026Q1 | 2 | Wednesday | 0
2026-01-08 | 2026 | 1 | January | 2026Q1 | 2 | Thursday | 0
2026-01-09 | 2026 | 1 | January | 2026Q1 | 2 | Friday | 0
2026-01-10 | 2026 | 1 | January | 2026Q1 | 2 | Saturday | 1
2026-01-11 | 2026 | 1 | January | 2026Q1 | 2 | Sunday | 1
2026-01-12 | 2026 | 1 | January | 2026Q1 | 3 | Monday | 0
2026-01-13 | 2026 | 1 | January | 2026Q1 | 3 | Tuesday | 0
2026-01-14 | 2026 | 1 | January | 2026Q1 | 3 | Wednesday | 0
2026-01-15 | 2026 | 1 | January | 2026Q1 | 3 | Thursday | 0
2026-01-16 | 2026 | 1 | January | 2026Q1 | 3 | Friday | 0
2026-01-17 | 2026 | 1 | January | 2026Q1 | 3 | Saturday | 1
2026-01-18 | 2026 | 1 | January | 2026Q1 | 3 | Sunday | 1
2026-01-19 | 2026 | 1 | January | 2026Q1 | 4 | Monday | 0
2026-01-20 | 2026 | 1 | January | 2026Q1 | 4 | Tuesday | 0
2026-01-21 | 2026 | 1 | January | 2026Q1 | 4 | Wednesday | 0
2026-01-22 | 2026 | 1 | January | 2026Q1 | 4 | Thursday | 0
2026-01-23 | 2026 | 1 | January | 2026Q1 | 4 | Friday | 0
2026-01-24 | 2026 | 1 | January | 2026Q1 | 4 | Saturday | 1
2026-01-25 | 2026 | 1 | January | 2026Q1 | 4 | Sunday | 1
2026-01-26 | 2026 | 1 | January | 2026Q1 | 5 | Monday | 0
2026-01-27 | 2026 | 1 | January | 2026Q1 | 5 | Tuesday | 0
2026-01-28 | 2026 | 1 | January | 2026Q1 | 5 | Wednesday | 0
2026-01-29 | 2026 | 1 | January | 2026Q1 | 5 | Thursday | 0
2026-01-30 | 2026 | 1 | January | 2026Q1 | 5 | Friday | 0
2026-01-31 | 2026 | 1 | January | 2026Q1 | 5 | Saturday | 1
2026-02-01 | 2026 | 2 | February | 2026Q1 | 5 | Sunday | 1
2026-02-02 | 2026 | 2 | February | 2026Q1 | 6 | Monday | 0
2026-02-03 | 2026 | 2 | February | 2026Q1 | 6 | Tuesday | 0
2026-02-04 | 2026 | 2 | February | 2026Q1 | 6 | Wednesday | 0
2026-02-05 | 2026 | 2 | February | 2026Q1 | 6 | Thursday | 0
2026-02-06 | 2026 | 2 | February | 2026Q1 | 6 | Friday | 0
2026-02-07 | 2026 | 2 | February | 2026Q1 | 6 | Saturday | 1
2026-02-08 | 2026 | 2 | February | 2026Q1 | 6 | Sunday | 1
2026-02-09 | 2026 | 2 | February | 2026Q1 | 7 | Monday | 0
2026-02-10 | 2026 | 2 | February | 2026Q1 | 7 | Tuesday | 0
2026-02-11 | 2026 | 2 | February | 2026Q1 | 7 | Wednesday | 0
2026-02-12 | 2026 | 2 | February | 2026Q1 | 7 | Thursday | 0
2026-02-13 | 2026 | 2 | February | 2026Q1 | 7 | Friday | 0
2026-02-14 | 2026 | 2 | February | 2026Q1 | 7 | Saturday | 1
2026-02-15 | 2026 | 2 | February | 2026Q1 | 7 | Sunday | 1
2026-02-16 | 2026 | 2 | February | 2026Q1 | 8 | Monday | 0
2026-02-17 | 2026 | 2 | February | 2026Q1 | 8 | Tuesday | 0
2026-02-18 | 2026 | 2 | February | 2026Q1 | 8 | Wednesday | 0
2026-02-19 | 2026 | 2 | February | 2026Q1 | 8 | Thursday | 0
2026-02-20 | 2026 | 2 | February | 2026Q1 | 8 | Friday | 0
2026-02-21 | 2026 | 2 | February | 2026Q1 | 8 | Saturday | 1
2026-02-22 | 2026 | 2 | February | 2026Q1 | 8 | Sunday | 1
2026-02-23 | 2026 | 2 | February | 2026Q1 | 9 | Monday | 0
2026-02-24 | 2026 | 2 | February | 2026Q1 | 9 | Tuesday | 0
2026-02-25 | 2026 | 2 | February | 2026Q1 | 9 | Wednesday | 0
2026-02-26 | 2026 | 2 | February | 2026Q1 | 9 | Thursday | 0
2026-02-27 | 2026 | 2 | February | 2026Q1 | 9 | Friday | 0
2026-02-28 | 2026 | 2 | February | 2026Q1 | 9 | Saturday | 1
2026-03-01 | 2026 | 3 | March | 2026Q1 | 9 | Sunday | 1
2026-03-02 | 2026 | 3 | March | 2026Q1 | 10 | Monday | 0
2026-03-03 | 2026 | 3 | March | 2026Q1 | 10 | Tuesday | 0
2026-03-04 | 2026 | 3 | March | 2026Q1 | 10 | Wednesday | 0
2026-03-05 | 2026 | 3 | March | 2026Q1 | 10 | Thursday | 0
2026-03-06 | 2026 | 3 | March | 2026Q1 | 10 | Friday | 0
2026-03-07 | 2026 | 3 | March | 2026Q1 | 10 | Saturday | 1
2026-03-08 | 2026 | 3 | March | 2026Q1 | 10 | Sunday | 1
2026-03-09 | 2026 | 3 | March | 2026Q1 | 11 | Monday | 0
2026-03-10 | 2026 | 3 | March | 2026Q1 | 11 | Tuesday | 0
2026-03-11 | 2026 | 3 | March | 2026Q1 | 11 | Wednesday | 0
2026-03-12 | 2026 | 3 | March | 2026Q1 | 11 | Thursday | 0
2026-03-13 | 2026 | 3 | March | 2026Q1 | 11 | Friday | 0
2026-03-14 | 2026 | 3 | March | 2026Q1 | 11 | Saturday | 1
2026-03-15 | 2026 | 3 | March | 2026Q1 | 11 | Sunday | 1
2026-03-16 | 2026 | 3 | March | 2026Q1 | 12 | Monday | 0
2026-03-17 | 2026 | 3 | March | 2026Q1 | 12 | Tuesday | 0
2026-03-18 | 2026 | 3 | March | 2026Q1 | 12 | Wednesday | 0
2026-03-19 | 2026 | 3 | March | 2026Q1 | 12 | Thursday | 0
2026-03-20 | 2026 | 3 | March | 2026Q1 | 12 | Friday | 0
2026-03-21 | 2026 | 3 | March | 2026Q1 | 12 | Saturday | 1
2026-03-22 | 2026 | 3 | March | 2026Q1 | 12 | Sunday | 1
2026-03-23 | 2026 | 3 | March | 2026Q1 | 13 | Monday | 0
2026-03-24 | 2026 | 3 | March | 2026Q1 | 13 | Tuesday | 0
2026-03-25 | 2026 | 3 | March | 2026Q1 | 13 | Wednesday | 0
2026-03-26 | 2026 | 3 | March | 2026Q1 | 13 | Thursday | 0
2026-03-27 | 2026 | 3 | March | 2026Q1 | 13 | Friday | 0
2026-03-28 | 2026 | 3 | March | 2026Q1 | 13 | Saturday | 1
2026-03-29 | 2026 | 3 | March | 2026Q1 | 13 | Sunday | 1
2026-03-30 | 2026 | 3 | March | 2026Q1 | 14 | Monday | 0
2026-03-31 | 2026 | 3 | March | 2026Q1 | 14 | Tuesday | 0
2026-04-01 | 2026 | 4 | April | 2026Q2 | 14 | Wednesday | 0
2026-04-02 | 2026 | 4 | April | 2026Q2 | 14 | Thursday | 0
2026-04-03 | 2026 | 4 | April | 2026Q2 | 14 | Friday | 0
2026-04-04 | 2026 | 4 | April | 2026Q2 | 14 | Saturday | 1
2026-04-05 | 2026 | 4 | April | 2026Q2 | 14 | Sunday | 1
2026-04-06 | 2026 | 4 | April | 2026Q2 | 15 | Monday | 0
2026-04-07 | 2026 | 4 | April | 2026Q2 | 15 | Tuesday | 0
2026-04-08 | 2026 | 4 | April | 2026Q2 | 15 | Wednesday | 0
2026-04-09 | 2026 | 4 | April | 2026Q2 | 15 | Thursday | 0
2026-04-10 | 2026 | 4 | April | 2026Q2 | 15 | Friday | 0
2026-04-11 | 2026 | 4 | April | 2026Q2 | 15 | Saturday | 1
2026-04-12 | 2026 | 4 | April | 2026Q2 | 15 | Sunday | 1
2026-04-13 | 2026 | 4 | April | 2026Q2 | 16 | Monday | 0
2026-04-14 | 2026 | 4 | April | 2026Q2 | 16 | Tuesday | 0
2026-04-15 | 2026 | 4 | April | 2026Q2 | 16 | Wednesday | 0
2026-04-16 | 2026 | 4 | April | 2026Q2 | 16 | Thursday | 0
2026-04-17 | 2026 | 4 | April | 2026Q2 | 16 | Friday | 0
2026-04-18 | 2026 | 4 | April | 2026Q2 | 16 | Saturday | 1
2026-04-19 | 2026 | 4 | April | 2026Q2 | 16 | Sunday | 1
2026-04-20 | 2026 | 4 | April | 2026Q2 | 17 | Monday | 0
2026-04-21 | 2026 | 4 | April | 2026Q2 | 17 | Tuesday | 0
2026-04-22 | 2026 | 4 | April | 2026Q2 | 17 | Wednesday | 0
2026-04-23 | 2026 | 4 | April | 2026Q2 | 17 | Thursday | 0
2026-04-24 | 2026 | 4 | April | 2026Q2 | 17 | Friday | 0
2026-04-25 | 2026 | 4 | April | 2026Q2 | 17 | Saturday | 1
2026-04-26 | 2026 | 4 | April | 2026Q2 | 17 | Sunday | 1
2026-04-27 | 2026 | 4 | April | 2026Q2 | 18 | Monday | 0
2026-04-28 | 2026 | 4 | April | 2026Q2 | 18 | Tuesday | 0
2026-04-29 | 2026 | 4 | April | 2026Q2 | 18 | Wednesday | 0
2026-04-30 | 2026 | 4 | April | 2026Q2 | 18 | Thursday | 0
2026-05-01 | 2026 | 5 | May | 2026Q2 | 18 | Friday | 0
2026-05-02 | 2026 | 5 | May | 2026Q2 | 18 | Saturday | 1
2026-05-03 | 2026 | 5 | May | 2026Q2 | 18 | Sunday | 1
2026-05-04 | 2026 | 5 | May | 2026Q2 | 19 | Monday | 0
2026-05-05 | 2026 | 5 | May | 2026Q2 | 19 | Tuesday | 0
2026-05-06 | 2026 | 5 | May | 2026Q2 | 19 | Wednesday | 0
2026-05-07 | 2026 | 5 | May | 2026Q2 | 19 | Thursday | 0
2026-05-08 | 2026 | 5 | May | 2026Q2 | 19 | Friday | 0
2026-05-09 | 2026 | 5 | May | 2026Q2 | 19 | Saturday | 1
2026-05-10 | 2026 | 5 | May | 2026Q2 | 19 | Sunday | 1
2026-05-11 | 2026 | 5 | May | 2026Q2 | 20 | Monday | 0
2026-05-12 | 2026 | 5 | May | 2026Q2 | 20 | Tuesday | 0
2026-05-13 | 2026 | 5 | May | 2026Q2 | 20 | Wednesday | 0
2026-05-14 | 2026 | 5 | May | 2026Q2 | 20 | Thursday | 0
2026-05-15 | 2026 | 5 | May | 2026Q2 | 20 | Friday | 0
2026-05-16 | 2026 | 5 | May | 2026Q2 | 20 | Saturday | 1
2026-05-17 | 2026 | 5 | May | 2026Q2 | 20 | Sunday | 1
2026-05-18 | 2026 | 5 | May | 2026Q2 | 21 | Monday | 0
2026-05-19 | 2026 | 5 | May | 2026Q2 | 21 | Tuesday | 0
2026-05-20 | 2026 | 5 | May | 2026Q2 | 21 | Wednesday | 0
2026-05-21 | 2026 | 5 | May | 2026Q2 | 21 | Thursday | 0
2026-05-22 | 2026 | 5 | May | 2026Q2 | 21 | Friday | 0
2026-05-23 | 2026 | 5 | May | 2026Q2 | 21 | Saturday | 1
2026-05-24 | 2026 | 5 | May | 2026Q2 | 21 | Sunday | 1
2026-05-25 | 2026 | 5 | May | 2026Q2 | 22 | Monday | 0
2026-05-26 | 2026 | 5 | May | 2026Q2 | 22 | Tuesday | 0
2026-05-27 | 2026 | 5 | May | 2026Q2 | 22 | Wednesday | 0
2026-05-28 | 2026 | 5 | May | 2026Q2 | 22 | Thursday | 0
2026-05-29 | 2026 | 5 | May | 2026Q2 | 22 | Friday | 0
2026-05-30 | 2026 | 5 | May | 2026Q2 | 22 | Saturday | 1
2026-05-31 | 2026 | 5 | May | 2026Q2 | 22 | Sunday | 1
2026-06-01 | 2026 | 6 | June | 2026Q2 | 23 | Monday | 0
2026-06-02 | 2026 | 6 | June | 2026Q2 | 23 | Tuesday | 0
2026-06-03 | 2026 | 6 | June | 2026Q2 | 23 | Wednesday | 0
2026-06-04 | 2026 | 6 | June | 2026Q2 | 23 | Thursday | 0
2026-06-05 | 2026 | 6 | June | 2026Q2 | 23 | Friday | 0
2026-06-06 | 2026 | 6 | June | 2026Q2 | 23 | Saturday | 1
2026-06-07 | 2026 | 6 | June | 2026Q2 | 23 | Sunday | 1
2026-06-08 | 2026 | 6 | June | 2026Q2 | 24 | Monday | 0
2026-06-09 | 2026 | 6 | June | 2026Q2 | 24 | Tuesday | 0
2026-06-10 | 2026 | 6 | June | 2026Q2 | 24 | Wednesday | 0
2026-06-11 | 2026 | 6 | June | 2026Q2 | 24 | Thursday | 0
2026-06-12 | 2026 | 6 | June | 2026Q2 | 24 | Friday | 0
2026-06-13 | 2026 | 6 | June | 2026Q2 | 24 | Saturday | 1
2026-06-14 | 2026 | 6 | June | 2026Q2 | 24 | Sunday | 1
2026-06-15 | 2026 | 6 | June | 2026Q2 | 25 | Monday | 0
2026-06-16 | 2026 | 6 | June | 2026Q2 | 25 | Tuesday | 0
2026-06-17 | 2026 | 6 | June | 2026Q2 | 25 | Wednesday | 0
2026-06-18 | 2026 | 6 | June | 2026Q2 | 25 | Thursday | 0
2026-06-19 | 2026 | 6 | June | 2026Q2 | 25 | Friday | 0
2026-06-20 | 2026 | 6 | June | 2026Q2 | 25 | Saturday | 1
2026-06-21 | 2026 | 6 | June | 2026Q2 | 25 | Sunday | 1
2026-06-22 | 2026 | 6 | June | 2026Q2 | 26 | Monday | 0
2026-06-23 | 2026 | 6 | June | 2026Q2 | 26 | Tuesday | 0
2026-06-24 | 2026 | 6 | June | 2026Q2 | 26 | Wednesday | 0
2026-06-25 | 2026 | 6 | June | 2026Q2 | 26 | Thursday | 0
2026-06-26 | 2026 | 6 | June | 2026Q2 | 26 | Friday | 0
2026-06-27 | 2026 | 6 | June | 2026Q2 | 26 | Saturday | 1
2026-06-28 | 2026 | 6 | June | 2026Q2 | 26 | Sunday | 1
2026-06-29 | 2026 | 6 | June | 2026Q2 | 27 | Monday | 0
2026-06-30 | 2026 | 6 | June | 2026Q2 | 27 | Tuesday | 0
2026-07-01 | 2026 | 7 | July | 2026Q3 | 27 | Wednesday | 0
2026-07-02 | 2026 | 7 | July | 2026Q3 | 27 | Thursday | 0
2026-07-03 | 2026 | 7 | July | 2026Q3 | 27 | Friday | 0
2026-07-04 | 2026 | 7 | July | 2026Q3 | 27 | Saturday | 1
2026-07-05 | 2026 | 7 | July | 2026Q3 | 27 | Sunday | 1
2026-07-06 | 2026 | 7 | July | 2026Q3 | 28 | Monday | 0
2026-07-07 | 2026 | 7 | July | 2026Q3 | 28 | Tuesday | 0
2026-07-08 | 2026 | 7 | July | 2026Q3 | 28 | Wednesday | 0
2026-07-09 | 2026 | 7 | July | 2026Q3 | 28 | Thursday | 0
2026-07-10 | 2026 | 7 | July | 2026Q3 | 28 | Friday | 0
2026-07-11 | 2026 | 7 | July | 2026Q3 | 28 | Saturday | 1
2026-07-12 | 2026 | 7 | July | 2026Q3 | 28 | Sunday | 1
2026-07-13 | 2026 | 7 | July | 2026Q3 | 29 | Monday | 0
2026-07-14 | 2026 | 7 | July | 2026Q3 | 29 | Tuesday | 0
2026-07-15 | 2026 | 7 | July | 2026Q3 | 29 | Wednesday | 0
2026-07-16 | 2026 | 7 | July | 2026Q3 | 29 | Thursday | 0
2026-07-17 | 2026 | 7 | July | 2026Q3 | 29 | Friday | 0
2026-07-18 | 2026 | 7 | July | 2026Q3 | 29 | Saturday | 1
2026-07-19 | 2026 | 7 | July | 2026Q3 | 29 | Sunday | 1
2026-07-20 | 2026 | 7 | July | 2026Q3 | 30 | Monday | 0
2026-07-21 | 2026 | 7 | July | 2026Q3 | 30 | Tuesday | 0
2026-07-22 | 2026 | 7 | July | 2026Q3 | 30 | Wednesday | 0
2026-07-23 | 2026 | 7 | July | 2026Q3 | 30 | Thursday | 0
2026-07-24 | 2026 | 7 | July | 2026Q3 | 30 | Friday | 0
2026-07-25 | 2026 | 7 | July | 2026Q3 | 30 | Saturday | 1
2026-07-26 | 2026 | 7 | July | 2026Q3 | 30 | Sunday | 1
2026-07-27 | 2026 | 7 | July | 2026Q3 | 31 | Monday | 0
2026-07-28 | 2026 | 7 | July | 2026Q3 | 31 | Tuesday | 0
2026-07-29 | 2026 | 7 | July | 2026Q3 | 31 | Wednesday | 0
2026-07-30 | 2026 | 7 | July | 2026Q3 | 31 | Thursday | 0
2026-07-31 | 2026 | 7 | July | 2026Q3 | 31 | Friday | 0
2026-08-01 | 2026 | 8 | August | 2026Q3 | 31 | Saturday | 1
2026-08-02 | 2026 | 8 | August | 2026Q3 | 31 | Sunday | 1
2026-08-03 | 2026 | 8 | August | 2026Q3 | 32 | Monday | 0
2026-08-04 | 2026 | 8 | August | 2026Q3 | 32 | Tuesday | 0
2026-08-05 | 2026 | 8 | August | 2026Q3 | 32 | Wednesday | 0
2026-08-06 | 2026 | 8 | August | 2026Q3 | 32 | Thursday | 0
2026-08-07 | 2026 | 8 | August | 2026Q3 | 32 | Friday | 0
2026-08-08 | 2026 | 8 | August | 2026Q3 | 32 | Saturday | 1
2026-08-09 | 2026 | 8 | August | 2026Q3 | 32 | Sunday | 1
2026-08-10 | 2026 | 8 | August | 2026Q3 | 33 | Monday | 0
2026-08-11 | 2026 | 8 | August | 2026Q3 | 33 | Tuesday | 0
2026-08-12 | 2026 | 8 | August | 2026Q3 | 33 | Wednesday | 0
2026-08-13 | 2026 | 8 | August | 2026Q3 | 33 | Thursday | 0
2026-08-14 | 2026 | 8 | August | 2026Q3 | 33 | Friday | 0
2026-08-15 | 2026 | 8 | August | 2026Q3 | 33 | Saturday | 1
2026-08-16 | 2026 | 8 | August | 2026Q3 | 33 | Sunday | 1
2026-08-17 | 2026 | 8 | August | 2026Q3 | 34 | Monday | 0
2026-08-18 | 2026 | 8 | August | 2026Q3 | 34 | Tuesday | 0
2026-08-19 | 2026 | 8 | August | 2026Q3 | 34 | Wednesday | 0
2026-08-20 | 2026 | 8 | August | 2026Q3 | 34 | Thursday | 0
2026-08-21 | 2026 | 8 | August | 2026Q3 | 34 | Friday | 0
2026-08-22 | 2026 | 8 | August | 2026Q3 | 34 | Saturday | 1
2026-08-23 | 2026 | 8 | August | 2026Q3 | 34 | Sunday | 1
2026-08-24 | 2026 | 8 | August | 2026Q3 | 35 | Monday | 0
2026-08-25 | 2026 | 8 | August | 2026Q3 | 35 | Tuesday | 0
2026-08-26 | 2026 | 8 | August | 2026Q3 | 35 | Wednesday | 0
2026-08-27 | 2026 | 8 | August | 2026Q3 | 35 | Thursday | 0
2026-08-28 | 2026 | 8 | August | 2026Q3 | 35 | Friday | 0
2026-08-29 | 2026 | 8 | August | 2026Q3 | 35 | Saturday | 1
2026-08-30 | 2026 | 8 | August | 2026Q3 | 35 | Sunday | 1
2026-08-31 | 2026 | 8 | August | 2026Q3 | 36 | Monday | 0
2026-09-01 | 2026 | 9 | September | 2026Q3 | 36 | Tuesday | 0
2026-09-02 | 2026 | 9 | September | 2026Q3 | 36 | Wednesday | 0
2026-09-03 | 2026 | 9 | September | 2026Q3 | 36 | Thursday | 0
2026-09-04 | 2026 | 9 | September | 2026Q3 | 36 | Friday | 0
2026-09-05 | 2026 | 9 | September | 2026Q3 | 36 | Saturday | 1
2026-09-06 | 2026 | 9 | September | 2026Q3 | 36 | Sunday | 1
2026-09-07 | 2026 | 9 | September | 2026Q3 | 37 | Monday | 0
2026-09-08 | 2026 | 9 | September | 2026Q3 | 37 | Tuesday | 0
2026-09-09 | 2026 | 9 | September | 2026Q3 | 37 | Wednesday | 0
2026-09-10 | 2026 | 9 | September | 2026Q3 | 37 | Thursday | 0
2026-09-11 | 2026 | 9 | September | 2026Q3 | 37 | Friday | 0
2026-09-12 | 2026 | 9 | September | 2026Q3 | 37 | Saturday | 1
2026-09-13 | 2026 | 9 | September | 2026Q3 | 37 | Sunday | 1
2026-09-14 | 2026 | 9 | September | 2026Q3 | 38 | Monday | 0
2026-09-15 | 2026 | 9 | September | 2026Q3 | 38 | Tuesday | 0
2026-09-16 | 2026 | 9 | September | 2026Q3 | 38 | Wednesday | 0
2026-09-17 | 2026 | 9 | September | 2026Q3 | 38 | Thursday | 0
2026-09-18 | 2026 | 9 | September | 2026Q3 | 38 | Friday | 0
2026-09-19 | 2026 | 9 | September | 2026Q3 | 38 | Saturday | 1
2026-09-20 | 2026 | 9 | September | 2026Q3 | 38 | Sunday | 1
2026-09-21 | 2026 | 9 | September | 2026Q3 | 39 | Monday | 0
2026-09-22 | 2026 | 9 | September | 2026Q3 | 39 | Tuesday | 0
2026-09-23 | 2026 | 9 | September | 2026Q3 | 39 | Wednesday | 0
2026-09-24 | 2026 | 9 | September | 2026Q3 | 39 | Thursday | 0
2026-09-25 | 2026 | 9 | September | 2026Q3 | 39 | Friday | 0
2026-09-26 | 2026 | 9 | September | 2026Q3 | 39 | Saturday | 1
2026-09-27 | 2026 | 9 | September | 2026Q3 | 39 | Sunday | 1
2026-09-28 | 2026 | 9 | September | 2026Q3 | 40 | Monday | 0
2026-09-29 | 2026 | 9 | September | 2026Q3 | 40 | Tuesday | 0
2026-09-30 | 2026 | 9 | September | 2026Q3 | 40 | Wednesday | 0
2026-10-01 | 2026 | 10 | October | 2026Q4 | 40 | Thursday | 0
2026-10-02 | 2026 | 10 | October | 2026Q4 | 40 | Friday | 0
2026-10-03 | 2026 | 10 | October | 2026Q4 | 40 | Saturday | 1
2026-10-04 | 2026 | 10 | October | 2026Q4 | 40 | Sunday | 1
2026-10-05 | 2026 | 10 | October | 2026Q4 | 41 | Monday | 0
2026-10-06 | 2026 | 10 | October | 2026Q4 | 41 | Tuesday | 0
2026-10-07 | 2026 | 10 | October | 2026Q4 | 41 | Wednesday | 0
2026-10-08 | 2026 | 10 | October | 2026Q4 | 41 | Thursday | 0
2026-10-09 | 2026 | 10 | October | 2026Q4 | 41 | Friday | 0
2026-10-10 | 2026 | 10 | October | 2026Q4 | 41 | Saturday | 1
2026-10-11 | 2026 | 10 | October | 2026Q4 | 41 | Sunday | 1
2026-10-12 | 2026 | 10 | October | 2026Q4 | 42 | Monday | 0
2026-10-13 | 2026 | 10 | October | 2026Q4 | 42 | Tuesday | 0
2026-10-14 | 2026 | 10 | October | 2026Q4 | 42 | Wednesday | 0
2026-10-15 | 2026 | 10 | October | 2026Q4 | 42 | Thursday | 0
2026-10-16 | 2026 | 10 | October | 2026Q4 | 42 | Friday | 0
2026-10-17 | 2026 | 10 | October | 2026Q4 | 42 | Saturday | 1
2026-10-18 | 2026 | 10 | October | 2026Q4 | 42 | Sunday | 1
2026-10-19 | 2026 | 10 | October | 2026Q4 | 43 | Monday | 0
2026-10-20 | 2026 | 10 | October | 2026Q4 | 43 | Tuesday | 0
2026-10-21 | 2026 | 10 | October | 2026Q4 | 43 | Wednesday | 0
2026-10-22 | 2026 | 10 | October | 2026Q4 | 43 | Thursday | 0
2026-10-23 | 2026 | 10 | October | 2026Q4 | 43 | Friday | 0
2026-10-24 | 2026 | 10 | October | 2026Q4 | 43 | Saturday | 1
2026-10-25 | 2026 | 10 | October | 2026Q4 | 43 | Sunday | 1
2026-10-26 | 2026 | 10 | October | 2026Q4 | 44 | Monday | 0
2026-10-27 | 2026 | 10 | October | 2026Q4 | 44 | Tuesday | 0
2026-10-28 | 2026 | 10 | October | 2026Q4 | 44 | Wednesday | 0
2026-10-29 | 2026 | 10 | October | 2026Q4 | 44 | Thursday | 0
2026-10-30 | 2026 | 10 | October | 2026Q4 | 44 | Friday | 0
2026-10-31 | 2026 | 10 | October | 2026Q4 | 44 | Saturday | 1
2026-11-01 | 2026 | 11 | November | 2026Q4 | 44 | Sunday | 1
2026-11-02 | 2026 | 11 | November | 2026Q4 | 45 | Monday | 0
2026-11-03 | 2026 | 11 | November | 2026Q4 | 45 | Tuesday | 0
2026-11-04 | 2026 | 11 | November | 2026Q4 | 45 | Wednesday | 0
2026-11-05 | 2026 | 11 | November | 2026Q4 | 45 | Thursday | 0
2026-11-06 | 2026 | 11 | November | 2026Q4 | 45 | Friday | 0
2026-11-07 | 2026 | 11 | November | 2026Q4 | 45 | Saturday | 1
2026-11-08 | 2026 | 11 | November | 2026Q4 | 45 | Sunday | 1
2026-11-09 | 2026 | 11 | November | 2026Q4 | 46 | Monday | 0
2026-11-10 | 2026 | 11 | November | 2026Q4 | 46 | Tuesday | 0
2026-11-11 | 2026 | 11 | November | 2026Q4 | 46 | Wednesday | 0
2026-11-12 | 2026 | 11 | November | 2026Q4 | 46 | Thursday | 0
2026-11-13 | 2026 | 11 | November | 2026Q4 | 46 | Friday | 0
2026-11-14 | 2026 | 11 | November | 2026Q4 | 46 | Saturday | 1
2026-11-15 | 2026 | 11 | November | 2026Q4 | 46 | Sunday | 1
2026-11-16 | 2026 | 11 | November | 2026Q4 | 47 | Monday | 0
2026-11-17 | 2026 | 11 | November | 2026Q4 | 47 | Tuesday | 0
2026-11-18 | 2026 | 11 | November | 2026Q4 | 47 | Wednesday | 0
2026-11-19 | 2026 | 11 | November | 2026Q4 | 47 | Thursday | 0
2026-11-20 | 2026 | 11 | November | 2026Q4 | 47 | Friday | 0
2026-11-21 | 2026 | 11 | November | 2026Q4 | 47 | Saturday | 1
2026-11-22 | 2026 | 11 | November | 2026Q4 | 47 | Sunday | 1
2026-11-23 | 2026 | 11 | November | 2026Q4 | 48 | Monday | 0
2026-11-24 | 2026 | 11 | November | 2026Q4 | 48 | Tuesday | 0
2026-11-25 | 2026 | 11 | November | 2026Q4 | 48 | Wednesday | 0
2026-11-26 | 2026 | 11 | November | 2026Q4 | 48 | Thursday | 0
2026-11-27 | 2026 | 11 | November | 2026Q4 | 48 | Friday | 0
2026-11-28 | 2026 | 11 | November | 2026Q4 | 48 | Saturday | 1
2026-11-29 | 2026 | 11 | November | 2026Q4 | 48 | Sunday | 1
2026-11-30 | 2026 | 11 | November | 2026Q4 | 49 | Monday | 0
2026-12-01 | 2026 | 12 | December | 2026Q4 | 49 | Tuesday | 0
2026-12-02 | 2026 | 12 | December | 2026Q4 | 49 | Wednesday | 0
2026-12-03 | 2026 | 12 | December | 2026Q4 | 49 | Thursday | 0
2026-12-04 | 2026 | 12 | December | 2026Q4 | 49 | Friday | 0
2026-12-05 | 2026 | 12 | December | 2026Q4 | 49 | Saturday | 1
2026-12-06 | 2026 | 12 | December | 2026Q4 | 49 | Sunday | 1
2026-12-07 | 2026 | 12 | December | 2026Q4 | 50 | Monday | 0
2026-12-08 | 2026 | 12 | December | 2026Q4 | 50 | Tuesday | 0
2026-12-09 | 2026 | 12 | December | 2026Q4 | 50 | Wednesday | 0
2026-12-10 | 2026 | 12 | December | 2026Q4 | 50 | Thursday | 0
2026-12-11 | 2026 | 12 | December | 2026Q4 | 50 | Friday | 0
2026-12-12 | 2026 | 12 | December | 2026Q4 | 50 | Saturday | 1
2026-12-13 | 2026 | 12 | December | 2026Q4 | 50 | Sunday | 1
2026-12-14 | 2026 | 12 | December | 2026Q4 | 51 | Monday | 0
2026-12-15 | 2026 | 12 | December | 2026Q4 | 51 | Tuesday | 0
2026-12-16 | 2026 | 12 | December | 2026Q4 | 51 | Wednesday | 0
2026-12-17 | 2026 | 12 | December | 2026Q4 | 51 | Thursday | 0
2026-12-18 | 2026 | 12 | December | 2026Q4 | 51 | Friday | 0
2026-12-19 | 2026 | 12 | December | 2026Q4 | 51 | Saturday | 1
2026-12-20 | 2026 | 12 | December | 2026Q4 | 51 | Sunday | 1
2026-12-21 | 2026 | 12 | December | 2026Q4 | 52 | Monday | 0
2026-12-22 | 2026 | 12 | December | 2026Q4 | 52 | Tuesday | 0
2026-12-23 | 2026 | 12 | December | 2026Q4 | 52 | Wednesday | 0
2026-12-24 | 2026 | 12 | December | 2026Q4 | 52 | Thursday | 0
2026-12-25 | 2026 | 12 | December | 2026Q4 | 52 | Friday | 0
2026-12-26 | 2026 | 12 | December | 2026Q4 | 52 | Saturday | 1
2026-12-27 | 2026 | 12 | December | 2026Q4 | 52 | Sunday | 1
2026-12-28 | 2026 | 12 | December | 2026Q4 | 53 | Monday | 0
2026-12-29 | 2026 | 12 | December | 2026Q4 | 53 | Tuesday | 0
2026-12-30 | 2026 | 12 | December | 2026Q4 | 53 | Wednesday | 0
2026-12-31 | 2026 | 12 | December | 2026Q4 | 53 | Thursday | 0
2027-01-01 | 2027 | 1 | January | 2027Q1 | 53 | Friday | 0
2027-01-02 | 2027 | 1 | January | 2027Q1 | 53 | Saturday | 1
2027-01-03 | 2027 | 1 | January | 2027Q1 | 53 | Sunday | 1
2027-01-04 | 2027 | 1 | January | 2027Q1 | 1 | Monday | 0
2027-01-05 | 2027 | 1 | January | 2027Q1 | 1 | Tuesday | 0
2027-01-06 | 2027 | 1 | January | 2027Q1 | 1 | Wednesday | 0
2027-01-07 | 2027 | 1 | January | 2027Q1 | 1 | Thursday | 0
2027-01-08 | 2027 | 1 | January | 2027Q1 | 1 | Friday | 0
2027-01-09 | 2027 | 1 | January | 2027Q1 | 1 | Saturday | 1
2027-01-10 | 2027 | 1 | January | 2027Q1 | 1 | Sunday | 1
2027-01-11 | 2027 | 1 | January | 2027Q1 | 2 | Monday | 0
2027-01-12 | 2027 | 1 | January | 2027Q1 | 2 | Tuesday | 0
2027-01-13 | 2027 | 1 | January | 2027Q1 | 2 | Wednesday | 0
2027-01-14 | 2027 | 1 | January | 2027Q1 | 2 | Thursday | 0
2027-01-15 | 2027 | 1 | January | 2027Q1 | 2 | Friday | 0
2027-01-16 | 2027 | 1 | January | 2027Q1 | 2 | Saturday | 1
2027-01-17 | 2027 | 1 | January | 2027Q1 | 2 | Sunday | 1
2027-01-18 | 2027 | 1 | January | 2027Q1 | 3 | Monday | 0
2027-01-19 | 2027 | 1 | January | 2027Q1 | 3 | Tuesday | 0
2027-01-20 | 2027 | 1 | January | 2027Q1 | 3 | Wednesday | 0
2027-01-21 | 2027 | 1 | January | 2027Q1 | 3 | Thursday | 0
2027-01-22 | 2027 | 1 | January | 2027Q1 | 3 | Friday | 0
2027-01-23 | 2027 | 1 | January | 2027Q1 | 3 | Saturday | 1
2027-01-24 | 2027 | 1 | January | 2027Q1 | 3 | Sunday | 1
2027-01-25 | 2027 | 1 | January | 2027Q1 | 4 | Monday | 0
2027-01-26 | 2027 | 1 | January | 2027Q1 | 4 | Tuesday | 0
2027-01-27 | 2027 | 1 | January | 2027Q1 | 4 | Wednesday | 0
2027-01-28 | 2027 | 1 | January | 2027Q1 | 4 | Thursday | 0
2027-01-29 | 2027 | 1 | January | 2027Q1 | 4 | Friday | 0
2027-01-30 | 2027 | 1 | January | 2027Q1 | 4 | Saturday | 1
2027-01-31 | 2027 | 1 | January | 2027Q1 | 4 | Sunday | 1
2027-02-01 | 2027 | 2 | February | 2027Q1 | 5 | Monday | 0
2027-02-02 | 2027 | 2 | February | 2027Q1 | 5 | Tuesday | 0
2027-02-03 | 2027 | 2 | February | 2027Q1 | 5 | Wednesday | 0
2027-02-04 | 2027 | 2 | February | 2027Q1 | 5 | Thursday | 0
2027-02-05 | 2027 | 2 | February | 2027Q1 | 5 | Friday | 0
2027-02-06 | 2027 | 2 | February | 2027Q1 | 5 | Saturday | 1
2027-02-07 | 2027 | 2 | February | 2027Q1 | 5 | Sunday | 1
2027-02-08 | 2027 | 2 | February | 2027Q1 | 6 | Monday | 0
2027-02-09 | 2027 | 2 | February | 2027Q1 | 6 | Tuesday | 0
2027-02-10 | 2027 | 2 | February | 2027Q1 | 6 | Wednesday | 0
2027-02-11 | 2027 | 2 | February | 2027Q1 | 6 | Thursday | 0
2027-02-12 | 2027 | 2 | February | 2027Q1 | 6 | Friday | 0
2027-02-13 | 2027 | 2 | February | 2027Q1 | 6 | Saturday | 1
2027-02-14 | 2027 | 2 | February | 2027Q1 | 6 | Sunday | 1
2027-02-15 | 2027 | 2 | February | 2027Q1 | 7 | Monday | 0
2027-02-16 | 2027 | 2 | February | 2027Q1 | 7 | Tuesday | 0
2027-02-17 | 2027 | 2 | February | 2027Q1 | 7 | Wednesday | 0
2027-02-18 | 2027 | 2 | February | 2027Q1 | 7 | Thursday | 0
2027-02-19 | 2027 | 2 | February | 2027Q1 | 7 | Friday | 0
2027-02-20 | 2027 | 2 | February | 2027Q1 | 7 | Saturday | 1
2027-02-21 | 2027 | 2 | February | 2027Q1 | 7 | Sunday | 1
2027-02-22 | 2027 | 2 | February | 2027Q1 | 8 | Monday | 0
2027-02-23 | 2027 | 2 | February | 2027Q1 | 8 | Tuesday | 0
2027-02-24 | 2027 | 2 | February | 2027Q1 | 8 | Wednesday | 0
2027-02-25 | 2027 | 2 | February | 2027Q1 | 8 | Thursday | 0
2027-02-26 | 2027 | 2 | February | 2027Q1 | 8 | Friday | 0
2027-02-27 | 2027 | 2 | February | 2027Q1 | 8 | Saturday | 1
2027-02-28 | 2027 | 2 | February | 2027Q1 | 8 | Sunday | 1
2027-03-01 | 2027 | 3 | March | 2027Q1 | 9 | Monday | 0
2027-03-02 | 2027 | 3 | March | 2027Q1 | 9 | Tuesday | 0
2027-03-03 | 2027 | 3 | March | 2027Q1 | 9 | Wednesday | 0
2027-03-04 | 2027 | 3 | March | 2027Q1 | 9 | Thursday | 0
2027-03-05 | 2027 | 3 | March | 2027Q1 | 9 | Friday | 0
2027-03-06 | 2027 | 3 | March | 2027Q1 | 9 | Saturday | 1
2027-03-07 | 2027 | 3 | March | 2027Q1 | 9 | Sunday | 1
2027-03-08 | 2027 | 3 | March | 2027Q1 | 10 | Monday | 0
2027-03-09 | 2027 | 3 | March | 2027Q1 | 10 | Tuesday | 0
2027-03-10 | 2027 | 3 | March | 2027Q1 | 10 | Wednesday | 0
2027-03-11 | 2027 | 3 | March | 2027Q1 | 10 | Thursday | 0
2027-03-12 | 2027 | 3 | March | 2027Q1 | 10 | Friday | 0
2027-03-13 | 2027 | 3 | March | 2027Q1 | 10 | Saturday | 1
2027-03-14 | 2027 | 3 | March | 2027Q1 | 10 | Sunday | 1
2027-03-15 | 2027 | 3 | March | 2027Q1 | 11 | Monday | 0
2027-03-16 | 2027 | 3 | March | 2027Q1 | 11 | Tuesday | 0
2027-03-17 | 2027 | 3 | March | 2027Q1 | 11 | Wednesday | 0
2027-03-18 | 2027 | 3 | March | 2027Q1 | 11 | Thursday | 0
2027-03-19 | 2027 | 3 | March | 2027Q1 | 11 | Friday | 0
2027-03-20 | 2027 | 3 | March | 2027Q1 | 11 | Saturday | 1
2027-03-21 | 2027 | 3 | March | 2027Q1 | 11 | Sunday | 1
2027-03-22 | 2027 | 3 | March | 2027Q1 | 12 | Monday | 0
2027-03-23 | 2027 | 3 | March | 2027Q1 | 12 | Tuesday | 0
2027-03-24 | 2027 | 3 | March | 2027Q1 | 12 | Wednesday | 0
2027-03-25 | 2027 | 3 | March | 2027Q1 | 12 | Thursday | 0
2027-03-26 | 2027 | 3 | March | 2027Q1 | 12 | Friday | 0
2027-03-27 | 2027 | 3 | March | 2027Q1 | 12 | Saturday | 1
2027-03-28 | 2027 | 3 | March | 2027Q1 | 12 | Sunday | 1
2027-03-29 | 2027 | 3 | March | 2027Q1 | 13 | Monday | 0
2027-03-30 | 2027 | 3 | March | 2027Q1 | 13 | Tuesday | 0
2027-03-31 | 2027 | 3 | March | 2027Q1 | 13 | Wednesday | 0
2027-04-01 | 2027 | 4 | April | 2027Q2 | 13 | Thursday | 0
2027-04-02 | 2027 | 4 | April | 2027Q2 | 13 | Friday | 0
2027-04-03 | 2027 | 4 | April | 2027Q2 | 13 | Saturday | 1
2027-04-04 | 2027 | 4 | April | 2027Q2 | 13 | Sunday | 1
2027-04-05 | 2027 | 4 | April | 2027Q2 | 14 | Monday | 0
2027-04-06 | 2027 | 4 | April | 2027Q2 | 14 | Tuesday | 0
2027-04-07 | 2027 | 4 | April | 2027Q2 | 14 | Wednesday | 0
2027-04-08 | 2027 | 4 | April | 2027Q2 | 14 | Thursday | 0
2027-04-09 | 2027 | 4 | April | 2027Q2 | 14 | Friday | 0
2027-04-10 | 2027 | 4 | April | 2027Q2 | 14 | Saturday | 1
2027-04-11 | 2027 | 4 | April | 2027Q2 | 14 | Sunday | 1
2027-04-12 | 2027 | 4 | April | 2027Q2 | 15 | Monday | 0
2027-04-13 | 2027 | 4 | April | 2027Q2 | 15 | Tuesday | 0
2027-04-14 | 2027 | 4 | April | 2027Q2 | 15 | Wednesday | 0
2027-04-15 | 2027 | 4 | April | 2027Q2 | 15 | Thursday | 0
2027-04-16 | 2027 | 4 | April | 2027Q2 | 15 | Friday | 0
2027-04-17 | 2027 | 4 | April | 2027Q2 | 15 | Saturday | 1
2027-04-18 | 2027 | 4 | April | 2027Q2 | 15 | Sunday | 1
2027-04-19 | 2027 | 4 | April | 2027Q2 | 16 | Monday | 0
2027-04-20 | 2027 | 4 | April | 2027Q2 | 16 | Tuesday | 0
2027-04-21 | 2027 | 4 | April | 2027Q2 | 16 | Wednesday | 0
2027-04-22 | 2027 | 4 | April | 2027Q2 | 16 | Thursday | 0
2027-04-23 | 2027 | 4 | April | 2027Q2 | 16 | Friday | 0
2027-04-24 | 2027 | 4 | April | 2027Q2 | 16 | Saturday | 1
2027-04-25 | 2027 | 4 | April | 2027Q2 | 16 | Sunday | 1
2027-04-26 | 2027 | 4 | April | 2027Q2 | 17 | Monday | 0
2027-04-27 | 2027 | 4 | April | 2027Q2 | 17 | Tuesday | 0
2027-04-28 | 2027 | 4 | April | 2027Q2 | 17 | Wednesday | 0
2027-04-29 | 2027 | 4 | April | 2027Q2 | 17 | Thursday | 0
2027-04-30 | 2027 | 4 | April | 2027Q2 | 17 | Friday | 0
2027-05-01 | 2027 | 5 | May | 2027Q2 | 17 | Saturday | 1
2027-05-02 | 2027 | 5 | May | 2027Q2 | 17 | Sunday | 1
2027-05-03 | 2027 | 5 | May | 2027Q2 | 18 | Monday | 0
2027-05-04 | 2027 | 5 | May | 2027Q2 | 18 | Tuesday | 0
2027-05-05 | 2027 | 5 | May | 2027Q2 | 18 | Wednesday | 0
2027-05-06 | 2027 | 5 | May | 2027Q2 | 18 | Thursday | 0
2027-05-07 | 2027 | 5 | May | 2027Q2 | 18 | Friday | 0
2027-05-08 | 2027 | 5 | May | 2027Q2 | 18 | Saturday | 1
2027-05-09 | 2027 | 5 | May | 2027Q2 | 18 | Sunday | 1
2027-05-10 | 2027 | 5 | May | 2027Q2 | 19 | Monday | 0
2027-05-11 | 2027 | 5 | May | 2027Q2 | 19 | Tuesday | 0
2027-05-12 | 2027 | 5 | May | 2027Q2 | 19 | Wednesday | 0
2027-05-13 | 2027 | 5 | May | 2027Q2 | 19 | Thursday | 0
2027-05-14 | 2027 | 5 | May | 2027Q2 | 19 | Friday | 0
2027-05-15 | 2027 | 5 | May | 2027Q2 | 19 | Saturday | 1
2027-05-16 | 2027 | 5 | May | 2027Q2 | 19 | Sunday | 1
2027-05-17 | 2027 | 5 | May | 2027Q2 | 20 | Monday | 0
2027-05-18 | 2027 | 5 | May | 2027Q2 | 20 | Tuesday | 0
2027-05-19 | 2027 | 5 | May | 2027Q2 | 20 | Wednesday | 0
2027-05-20 | 2027 | 5 | May | 2027Q2 | 20 | Thursday | 0
2027-05-21 | 2027 | 5 | May | 2027Q2 | 20 | Friday | 0
2027-05-22 | 2027 | 5 | May | 2027Q2 | 20 | Saturday | 1
2027-05-23 | 2027 | 5 | May | 2027Q2 | 20 | Sunday | 1
2027-05-24 | 2027 | 5 | May | 2027Q2 | 21 | Monday | 0
2027-05-25 | 2027 | 5 | May | 2027Q2 | 21 | Tuesday | 0
2027-05-26 | 2027 | 5 | May | 2027Q2 | 21 | Wednesday | 0

## BridgeDependencies
CompanyID | CompanyTaskID | DependsOnCompanyTaskID
1 | INV-005@1 | INV-001@1
1 | VAT-002@1 | FIN-003@1
1 | GOL-003@1 | TST-003@1
1 | TST-003@1 | MIG-003@1
1 | MIG-003@1 | INV-005@1
2 | INV-005@2 | INV-001@2
2 | VAT-002@2 | FIN-003@2
2 | GOL-003@2 | TST-003@2
2 | TST-003@2 | MIG-003@2
2 | MIG-003@2 | INV-005@2
3 | INV-005@3 | INV-001@3
3 | VAT-002@3 | FIN-003@3
3 | GOL-003@3 | TST-003@3
3 | TST-003@3 | MIG-003@3
3 | MIG-003@3 | INV-005@3

## Milestones
CompanyID | CompanyMilestoneID | MilestoneID | Milestone | TargetDate
1 | MS-001@1 | MS-001 | Sandbox ready | 2026-05-19
1 | MS-002@1 | MS-002 | UAT sign-off | 2026-06-21
1 | MS-003@1 | MS-003 | Go-live | 2026-06-29
2 | MS-001@2 | MS-001 | Sandbox ready | 2026-06-18
2 | MS-002@2 | MS-002 | UAT sign-off | 2026-07-21
2 | MS-003@2 | MS-003 | Go-live | 2026-07-29
3 | MS-001@3 | MS-001 | Sandbox ready | 2026-07-18
3 | MS-002@3 | MS-002 | UAT sign-off | 2026-08-20
3 | MS-003@3 | MS-003 | Go-live | 2026-08-28

## Measures_Catalogue
MeasureName | DAX | Description
Total Tasks | COUNTROWS(FactTasks) | Count of tasks
Completed Tasks | CALCULATE([Total Tasks], DimStatus[IsClosed] = 1) | Closed tasks
Open Tasks | [Total Tasks]-[Completed Tasks] | Open tasks
Completion % | DIVIDE([Completed Tasks],[Total Tasks]) | Overall completion
Overdue Tasks | CALCULATE([Total Tasks], FactTasks[DueDate] < TODAY() && DimStatus[IsClosed] = 0) | Overdue
Companies | DISTINCTCOUNT(DimCompany[CompanyID]) | Number of companies
Completion % by Company | DIVIDE(CALCULATE([Completed Tasks], ALLEXCEPT(DimCompany, DimCompany[CompanyID])), CALCULATE([Total Tasks], ALLEXCEPT(DimCompany, DimCompany[CompanyID]))) | Completion per company

## Dashboard_Layout
PageOrder | PageName | Visuals
1 | Portfolio Overview | KPI cards: Companies, Completion %, Overdue Tasks; matrix: Company x RAG; bar: Completion % by company; bar: Overdue by company; table: Blocked tasks
2 | Executive Summary | KPI cards: Total Tasks, Completion %, Overdue %; bar: tasks by status; bar: tasks by module; line: completion over time
3 | Company Drillthrough | Drillthrough page filtered by Company: Gantt-ish table, tasks by module, milestones
4 | Risks & Issues | Table of blocked/high risk tasks; donut risk split; bar blocked by module